## Testcases
Last Modifed | 2016-08-10
ID | UseCaseID | Device | Test Case Description | Expected Result
1 | UC-1 | Both | At login screen, check the availability of sign up menu and check the functionality of sign up menu | There is sign up button or link is available and if user select the button, user can enter their information to sign up
2 | UC-1 | Both | If some required field is unfilled, check the submit button | If user miss some required field at the sign up form, submit button should be inactive At mobile, after user select submit, it will be notified required field is not filled
3 | UC-1 | Both | Filling out sign up form and submit the form | There is a message feedback after user successfully submit the register form. After signing up, user can log in the system automatically
4 | UC-1 | Both | After signup at mobile, try to sign in at web app with the same account | User can login at web app
5 | UC-1 | Web | SignUp page | When user clicks SignUp link, move to SignUp page. User resgister with only email and password
6 | UC-1 | Web | SignUp, Clicking 'SignUp' button | Email, password input values are validate. Invalid value exist, pop-up message will be showing to notify
7 | UC-1 | Both | After signup at web app, try to sign in at mobile app with same account | User can login at mobile app
8 | UC-2 | Web | Login, check input validation of email and password | Invalid input values are not allowed and shows message to User
9 | UC-2 | Web | Login, 'Log In' button is disable | User input valid value at email and password input box then 'Log In' button turns enable to perform login
10 | UC-2 | Web | Loggedin successfully | redirect to user dashboard page
11 | UC-2 | Web | Clicking Logout | User access token is delete and redirect to home page (about page)
12 | UC-3 | Mobile | Exit with autologin checkbox checked, and try to rerun the app | User can login automatically without asking login ID
13 | UC-3 | Mobile | Uncheck the autologin checkbox and exit the app Run the application and check login screen | User login screen should be shown
14 | UC-3 | Mobile | Reinstall the mobile application and try to login with the same account | User can login with the same account
15 | UC-4 | Mobile | After login, check the screen | At initial state , No Receipt screen will be shown After adding receipt, list of receipt will be shown
16 | UC-4 | Mobile | Check the item of list | Receipt information will have date, store, category, total, tag, receipt image, status of sync
17 | UC-4 | Mobile | Select the item of list | If the item of list is selected, detail view of receipt will be shown
18 | UC-4 | Mobile | Long Click on the item of list | Dialog popup will be shown to get confirm to delete the item
19 | UC-4 | Web | Receipts, show user's receipt data | retrieve from receipts data from database with pagination
20 | UC-4 | Web | Receipts, pagination function | Previous and Next button work correctly, page unit works correctly
21 | UC-4 | Web | Receipts, Search function | When user input value in search text, it filters and show the result in the table correctly
22 | UC-4 | Web | Receipts, Sorted by clicking each table title | Except comment, sorted by store name, data, total, number of items out of receipts list
23 | UC-4 | Web | Receipts, Export Excel file function | When user clicks 'Export Excel' icon, downloading the excel file including contents of table
24 | UC-5 | Mobile | Check detailed view of receipt | The detailed view will have image of the receipt, store name, date of purchase, category, tag, comment, total, payment method. Edit button will be shown at the bottom
25 | UC-5 | Web | View Receipt, Show data and image of receipt | Display data from database, and show image of photo if attached
26 | UC-5 | Web | View Receipt, clicking 'Edit button' | Move to Edit Page with related data of the receipt
27 | UC-5 | Web | View Receipt, clicking 'Tag's button related with the receipt | Pop-up window to show receipts list related with selected tag
28 | UC-5 | Web | View Receipt, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt
29 | UC-5 | Web | Unauthorized user trys to access loggedin pages | redirect to the 'Login' pages
30 | UC-5 | Both | Select one of items for viewing details | At detail, it will show receipt's detail information such as date of purchase, store, category, total, comment, tag, picture of receipt.
31 | UC-6 | Web | Add Receipt, Data editable | Store, Category, Price, Number of items are required and validation check. Comment is optional, but only allowed 140 letters length. Other required input value will be validated, when invalid value exist, pop-up message to notice.
32 | UC-6 | Web | Add Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data
33 | UC-6 | Mobile | At mobile, go to the menu of create receipt | The phone will be in preview state of taking picture
34 | UC-6 | Mobile | Check preview screen | There shoule be some feedback to the user to help taking picture of receipt for better character recognition
35 | UC-6 | Mobile | There's menu to take picture | If user select taking picture, result of character recognition for total and store name will be presented to the user And User can edit the information
36 | UC-6 | Mobile | Save the result | After saving the information, there's feedback it was saved succssfully or not and will be redirected to the list of receipt
37 | UC-6 | Mobile | Scan a receipt for a store listed in the autocomplete | After taking photo, the correct store name is found by OCR.
38 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete | After taking photo, the correct payment method is found by OCR.
39 | UC-6 | Mobile | Scan a receipt with a store name not found in the autocomplete | First line of text is suggested as store name
40 | UC-6 | Mobile | Scan a receipt with a store name not found in autocomplete and allow user to add new store name | After taking photo, on Add Receipt screen a store name can be edited and added
41 | UC-6 | Mobile | Scan a receipt and make sure total is found by O.C.R. | The total is found and completed by the O.C.R.
42 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete but change it before saving | The user can change a payment method before saving
43 | UC-6 | Mobile | Make sure the image of a receipt is saved after scanning | Bounding boxes are removed from the image
44 | UC-6 | Mobile | During scanning of image before taking photo, display results found so far for user to see | The displayed indicators should be in synchronization with the ocr result
45 | UC-6 | Mobile | Scan a store name printed with stylized text, logo, etc. | O.C.R. should be able to recognize some special fonts, not always but at least some cases should work.
46 | UC-6 | Mobile | Scan a receipt with a date that includes the month fully written out, i.e. "January", "July", etc. | All parts of the date should be found by the O.C.R.
47 | UC-6 | Mobile | Scan a receipt with a date of format dd-mm-yyyy | The O.C.R. should recognize the '-' delimiter and process the date
48 | UC-6 | Mobile | Scan a receipt with a date of format dd/mm/yyyy | The O.C.R. should recognize the '/' delimiter and process the date
49 | UC-6 | Mobile | Scan a receipt with a date that includes three letters of the month written out, i.e. "Jan", "Jul", etc. | The O.C.R. should find the date and scan it correctly
50 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm-dd-yyyy | The O.C.R. should recognize the '-' delimiter and process the date
51 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm/dd/yyyy | The O.C.R. should recognize the '/' delimiter and process the date
52 | UC-6 | Mobile | Cacel the result | If user select cancel instead of save, it will go to the preview status
53 | UC-7 | Mobile | Select edit button at detail view | Edit screen of the receipt will be shown
54 | UC-7 | Mobile | Modify value at edit view and save | Modified value should be applied and it will goto list view
55 | UC-7 | Mobile | At mobile, go to edit recipt information which is presented at list view of receipt or detail view of receipt | User can edit receipt information manually and after saving it will go to previous state.
56 | UC-7 | Both | After Sync, check the updated information at web app | After sync, updated receipt information can be seen at Web app
57 | UC-7 | Web | Edit Receipt, Data editable | Store, Category, Price, Number of items, comment, image of receipt are editable
58 | UC-7 | Web | Edit Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data
59 | UC-7 | Web | Edit Receipt, validation of input values | Editable values are validated where each of values is valid or not
60 | UC-7 | Web | Edit Receipt, uploading image file of receipt | Allow image type files are allowed to be uploaded and validate less than 2MB file size
61 | UC-8 | Mobile | Delete one of items and check the list of recipt | User can delete one or more receipt at the receipt list or receipt detail
62 | UC-8 | Web | Edit Receipt, Clicking 'Delete Receipt' button | pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete receipt and remove relation with related with data and then redirect to 'Receipts' page. When clicking 'Cancel', close pop up window and back to Edit Receipt page
63 | UC-9 | Both | Search one recipt with keyword at the search menu box | User can search receipt by keywords
64 | UC-9 | Both | Select a filter at the list | User can filter receipt by store, category, date
65 | UC-10 | Web | Categories, clicking 'Config-Categories' menu in the navigation bar | Shows user's customizing category data which retrieved from database with pagination
66 | UC-10 | Web | Categories, pagination function | Previous and Next button work correctly, page unit works correctly
67 | UC-10 | Web | Categories, Search function | When user input value in search text, it filters and show the result in the table correctly
68 | UC-10 | Web | Categories, Sorted by clicking category name | sorted by category name as descending or ascending
69 | UC-10 | Web | Categories, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected category
70 | UC-10 | Web | Categories, Clicking 'Add Category' button | Move to Add Page
71 | UC-10 | Web | Add Category, input category name | User is allow to input category name, but validate invalid input value such empty value, already existing name
72 | UC-10 | Web | Add Category, Clicking 'Save Category' button | if category name is valid, 'Save Category' button is enabled, after clicking 'Save Category' button, store new category name into database, and then redirect to 'Categories' page
73 | UC-10 | Web | Edit Category, 'Delete Category' button is disabled | When category is used by store(s), user is not allowed to delete category, so 'Delete Category' button is disabled
74 | UC-10 | Web | Edit Category, Edit Category Name | Category Name is editable, but validate invalid input value such empty value, already existing name
75 | UC-10 | Web | Edit Category, Clicking 'Save Category' button | Save category name and redirect to 'Categories' page
76 | UC-10 | Web | Edit Category, Clicking 'Delete Category' | When clicking enabled 'Delete Category', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete catgory and then redirect to 'Categories' page. When clicking 'Cancel', close the pop up window and back to Edit Category page
77 | UC-10 | Web | Tags, clicking 'Config-Tags' menu in the navigation bar | Shows user's customizing tag data which retrieved from database with pagination
78 | UC-10 | Web | Tags, pagination function | Previous and Next button work correctly, page unit works correctly
79 | UC-10 | Web | Tags, Search function | When user input value in search text, it filters and show the result in the table correctly
80 | UC-10 | Web | Tags, Sorted by clicking category name | sorted by tag name as descending or ascending
81 | UC-10 | Web | Tags, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected tag
82 | UC-10 | Web | Tags, Clicking 'Add Tag' button | Move to Add Page
83 | UC-10 | Web | Add Tag, input tag name | User is allow to input tag name, but validate invalid input value such empty value, already existing name
84 | UC-10 | Web | Add Tag, Clicking 'Save Tag' button | if tag name is valid, 'Save Tag' button is enabled, after clicking 'Save Tag' button, store new tag name into database, and then redirect to 'Tags' page
85 | UC-10 | Web | Edit Tag, 'DeleteTag' button is disabled | When tag is used by receipt(s), user is not allowed to delete tag, so 'Delete Tag' button is disabled
86 | UC-10 | Web | Edit Tag, Edit Tag Name | Tag Name is editable, but validate invalid input value such empty value, already existing name
87 | UC-10 | Web | Edit Tag, Clicking 'Save Tag' button | Save tag name and redirect to 'Tags' page
88 | UC-10 | Web | Edit Tag, Clicking 'Delete Tag' | When clicking enabled 'Delete Tag', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete tag and then redirect to 'Tags' page. When clicking 'Cancel', close the pop up window and back to Edit Tag page
89 | UC-10 | Web | Stores, clicking 'Config-Stores' menu in the navigation bar | Shows user's customizing store data which retrieved from database with pagination
90 | UC-10 | Web | Stores, pagination function | Previous and Next button work correctly, page unit works correctly
91 | UC-10 | Web | Stores, Search function | When user input value in search text, it filters and show the result in the table correctly
92 | UC-10 | Web | Stores, Sorted by clicking store name | sorted by store name as descending or ascending
93 | UC-10 | Web | Stores, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected store
94 | UC-10 | Web | Stores, Clicking 'Add Store' button | Move to Add Page
95 | UC-10 | Web | Add Store, input store name | User is allow to input store name and select category, but validate invalid input value such empty value, already existing name, and if category is selected or not
96 | UC-10 | Web | Add Store, Clicking 'Save Store' button | if store name is valid, 'Save Store' button is enabled, after clicking 'Save Store' button, save new store name with relation to category into database, and then redirect to 'Stores' page
97 | UC-10 | Web | Edit Store, 'Delete Store' button is disabled | When store is used by receipt(s), user is not allowed to delete store, so 'Delete Store' button is disabled
98 | UC-10 | Web | Edit Store, Edit Store Name and select category name | Store name is editable and allow to re-select category accordingly, but validate invalid input value such empty value, already existing name, and if category is selected or not
100 | UC-10 | Web | Edit Store, Clicking 'Save Store' button | Save store name and redirect to 'Stores' page
101 | UC-10 | Web | Edit Store, Clicking 'Delete Store' | When clicking enabled 'Delete Store', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete store with disconnecting relation to category and then redirect to 'Stores' page. When clicking 'Cancel', close the pop up window and back to Edit Store page
102 | UC-10 | Both | Select Adding Tag at the receipt list | User can add tag at the list of receipt or detail view of receipt
103 | UC-10 | Both | Select Addinng Category for the store | There is a menu for adding or modifying store's category
104 | UC-11 | Web | Chart, Clicking 'chart' menu link in the navigation bar | Move to 'Charts' page and display various type of chars and graphs. Monthly consumption, Comparison bar chart, Tag tendency, Store Amount, Category, Store, Tag, and Tag Progress Bar chart which are all retrived from database
105 | UC-11 | Web | Chart, Changing the period of month in 'Montly consumption' title bar | Changing all charts and graphs according to selected period of months and display data that retrieve from database
106 | UC-11 | Web | Chart, Moving mouse on the each value of chart or graph | Pop up the tooltip and show the value of each chart or graph
107 | UC-11 | Web | Chart, Clicking pdf icon button on the right top of the title bar | Download pdf file as selected chart in Monthly comsumption, Comparison, Tag Tendancy, and Store Amount Charts
108 | UC-12 | Web | Dashboard, displaying each data | data retrieve from database correctly, if no data in database show no data in it
109 | UC-12 | Web | Dashboard, chart can export to several types of tiles | Export chart to Print, PDF, JPEG, PNG, SVG files
110 | UC-12 | Web | Dashboard, edit user's basic profile and change password | User can modify username, firstname, lastname, user potho, and changing password
111 | UC-12 | Web | Dashboard, upload user's photo in user profile pop-up window | Only allows image type of file and validate less than 2MB file size, if invalid shows message to user
112 | UC-12 | Web | Dashboard, clicking each of tag name in Tags cloud section | Pop-up window to show receipts list related with selected tag
113 | UC-12 | Web | Dashboard, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt
114 | UC-13 | Web | Groups, Clicking 'Groups' on the navigation bar | Move to 'Groups' page
115 | UC-13 | Web | Groups, showing group information | If user has user's already created group, then display group name as owner. If user has joined group(s) as a member, then display joined group(s) name
116 | UC-13 | Web | Groups, Clicking 'Add Group' button | When user haven't created a group, 'Add Group' button is visible. After clicking 'Add Group' button, move to 'Add Group' page
117 | UC-13 | Web | Add Group, input group name, group description | Group name is required and description is optional. Validating group name such as empty value and less than 30 letters. Also description is limited less than 140 letters
118 | UC-13 | Web | Add Group, Clicking 'Save Group' button | Save group name and descript and redirect to 'Groups' page
119 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as owner' | Move to eighter of 'Group Receipts', 'View Group', or 'Edit Group' pages
120 | UC-13 | Web | View Group, show group detailed information | display data from database, and show member(s) email list if the group has member(s). If the loggedin user is an owner of group, shows additional buttons such as 'Edit Group', 'Group Categories', 'Group Stores', and 'Group Tags'
121 | UC-13 | Web | View Group, clicking each of buttons | move to related pages such as 'Group Receipts', 'Group Charts'
122 | UC-13 | Web | Edit Group, edit group name, description | Group name and description is editable
123 | UC-13 | Web | Edit Group, 'Delete Group' is disabled | If group already has member(s), owner is not allowed to delete group, so the 'Delete Group' button is disabled
124 | UC-13 | Web | Edit Group, Clicking 'Invitation' button | Group owner is allowed to invite user as group member with email, after clicking 'Invitation' button, email is added in the 'Invitation list'
125 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Invitation list' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Invitation list'. When clicking 'Cancel', close the pop up window and back to Edit Group page
126 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Leaving Group' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Leaving Group'. The member will not show any more When clicking 'Cancel', close the pop up window and back to Edit Group page
127 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as member' | Move to relevent page in case of 'Receipt' and 'View Details'
128 | UC-13 | Web | Groups, Clicking 'Leave Group' font icon button in 'Group as member' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, send request notification to group owner. When clicking 'Cancel', close the pop up window and back to Group page
129 | UC-13 | Web | Groups, Showing notification | Member can receive notification from group owner's invitation as member
130 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user
131 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving
132 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving
134 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user
135 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving
136 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving

## Iteration1
Schedule
Planned Start Date |  | Planned End Date |  | Actual Start Date |  | Actual End Date
2016-06-24 |  | 2016-06-26 |  | 2016-06-24 |  | 2016-06-26
SUM
Total TC | Tested TC (Except N/A) | Total Pass |  | Total N/A | Pass Rate
131 | 131 | 59 |  | 67 | 45.04%
ID | UseCaseID | Device | Test Case Description | Expected Result | Actual Result Description | Pass/N/A
1 | UC-1 | Both | At login screen, check the availability of sign up menu and check the functionality of sign up menu | There is sign up button or link is available and if user select the button, user can enter their information to sign up |  | Pass
2 | UC-1 | Both | If some required field is unfilled, check the submit button | If user miss some required field at the sign up form, submit button should be inactive At mobile, after user select submit, it will be notified required field is not filled |  | Pass
3 | UC-1 | Both | Filling out sign up form and submit the form | There is a message feedback after user successfully submit the register form. After signing up, user can log in the system automatically |  | Pass
4 | UC-1 | Both | After signup at mobile, try to sign in at web app with the same account | User can login at web app |  | Pass
5 | UC-1 | Web | SignUp page | When user clicks SignUp link, move to SignUp page. User resgister with only email and password | Works as expected | Pass
6 | UC-1 | Web | SignUp, Clicking 'SignUp' button | Email, password input values are validate. Invalid value exist, pop-up message will be showing to notify | Works as expected | Pass
7 | UC-1 | Both | After signup at web app, try to sign in at mobile app with same account | User can login at mobile app |  | Pass
8 | UC-2 | Web | Login, check input validation of email and password | Invalid input values are not allowed and shows message to User | Works as expected | Pass
9 | UC-2 | Web | Login, 'Log In' button is disable | User input valid value at email and password input box then 'Log In' button turns enable to perform login | Works as expected | Pass
10 | UC-2 | Web | Loggedin successfully | redirect to user dashboard page | Works as expected | Pass
11 | UC-2 | Web | Clicking Logout | User access token is delete and redirect to home page (about page) | Works as expected | Pass
12 | UC-3 | Mobile | Exit with autologin checkbox checked, and try to rerun the app | User can login automatically without asking login ID |  | Pass
13 | UC-3 | Mobile | Uncheck the autologin checkbox and exit the app Run the application and check login screen | User login screen should be shown |  | Pass
14 | UC-3 | Mobile | Reinstall the mobile application and try to login with the same account | User can login with the same account |  | Pass
15 | UC-4 | Mobile | After login, check the screen | At initial state , No Receipt screen will be shown After adding receipt, list of receipt will be shown |  | Pass
16 | UC-4 | Mobile | Check the item of list | Receipt information will have date, store, category, total, tag, receipt image, status of sync |  | Pass
17 | UC-4 | Mobile | Select the item of list | If the item of list is selected, detail view of receipt will be shown |  | Pass
18 | UC-4 | Mobile | Long Click on the item of list | Dialog popup will be shown to get confirm to delete the item |  | Pass
19 | UC-4 | Web | Receipts, show user's receipt data | retrieve from receipts data from database with pagination | Not implemented | N/A
20 | UC-4 | Web | Receipts, pagination function | Previous and Next button work correctly, page unit works correctly | Not implemented | N/A
21 | UC-4 | Web | Receipts, Search function | When user input value in search text, it filters and show the result in the table correctly | Not implemented | N/A
22 | UC-4 | Web | Receipts, Sorted by clicking each table title | Except comment, sorted by store name, data, total, number of items out of receipts list | Not implemented | N/A
23 | UC-4 | Web | Receipts, Export Excel file function | When user clicks 'Export Excel' icon, downloading the excel file including contents of table | Not implemented | N/A
24 | UC-5 | Mobile | Check detailed view of receipt | The detailed view will have image of the receipt, store name, date of purchase, category, tag, comment, total, payment method. Edit button will be shown at the bottom |  | Pass
25 | UC-5 | Web | View Receipt, Show data and image of receipt | Display data from database, and show image of photo if attached | Not implemented | N/A
26 | UC-5 | Web | View Receipt, clicking 'Edit button' | Move to Edit Page with related data of the receipt | Not implemented | N/A
27 | UC-5 | Web | View Receipt, clicking 'Tag's button related with the receipt | Pop-up window to show receipts list related with selected tag | Not implemented | N/A
28 | UC-5 | Web | View Receipt, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt | Not implemented | N/A
29 | UC-5 | Web | Unauthorized user trys to access loggedin pages | redirect to the 'Login' pages | Works as expected | Pass
30 | UC-5 | Both | Select one of items for viewing details | At detail, it will show receipt's detail information such as date of purchase, store, category, total, comment, tag, picture of receipt. |  | Pass
31 | UC-6 | Web | Add Receipt, Data editable | Store, Category, Price, Number of items are required and validation check. Comment is optional, but only allowed 140 letters length. Other required input value will be validated, when invalid value exist, pop-up message to notice. | Not implemented | N/A
32 | UC-6 | Web | Add Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Not implemented | N/A
33 | UC-6 | Mobile | At mobile, go to the menu of create receipt | The phone will be in preview state of taking picture |  | Pass
34 | UC-6 | Mobile | Check preview screen | There shoule be some feedback to the user to help taking picture of receipt for better character recognition |  | Pass
35 | UC-6 | Mobile | There's menu to take picture | If user select taking picture, result of character recognition for total and store name will be presented to the user And User can edit the information |  | Pass
36 | UC-6 | Mobile | Save the result | After saving the information, there's feedback it was saved succssfully or not and will be redirected to the list of receipt |  | Pass
37 | UC-6 | Mobile | Scan a receipt for a store listed in the autocomplete | After taking photo, the correct store name is found by OCR. |  | Pass
38 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete | After taking photo, the correct payment method is found by OCR. |  | N/A
39 | UC-6 | Mobile | Scan a receipt with a store name not found in the autocomplete | First line of text is suggested as store name |  | N/A
40 | UC-6 | Mobile | Scan a receipt with a store name not found in autocomplete and allow user to add new store name | After taking photo, on Add Receipt screen a store name can be edited and added |  | N/A
41 | UC-6 | Mobile | Scan a receipt and make sure total is found by O.C.R. | The total is found and completed by the O.C.R. | Someatimes subtotal is found by mistake | Fail
42 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete but change it before saving | The user can change a payment method before saving |  | N/A
43 | UC-6 | Mobile | Make sure the image of a receipt is saved after scanning | Bounding boxes are removed from the image | Image is saved but bounding boxes still present | Fail
44 | UC-6 | Mobile | During scanning of image before taking photo, display results found so far for user to see | The displayed indicators should be in synchronization with the ocr result | Data displayed does not always update when result changes | Fail
45 | UC-6 | Mobile | Scan a store name printed with stylized text, logo, etc. | O.C.R. should be able to recognize some special fonts, not always but at least some cases should work. |  | N/A
46 | UC-6 | Mobile | Scan a receipt with a date that includes the month fully written out, i.e. "January", "July", etc. | All parts of the date should be found by the O.C.R. |  | N/A
47 | UC-6 | Mobile | Scan a receipt with a date of format dd-mm-yyyy | The O.C.R. should recognize the '-' delimiter and process the date | Date not found | Fail
48 | UC-6 | Mobile | Scan a receipt with a date of format dd/mm/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Date not found | Fail
49 | UC-6 | Mobile | Scan a receipt with a date that includes three letters of the month written out, i.e. "Jan", "Jul", etc. | The O.C.R. should find the date and scan it correctly |  | Pass
50 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm-dd-yyyy | The O.C.R. should recognize the '-' delimiter and process the date | Works as expected | Pass
51 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm/dd/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Works as expected | Pass
52 | UC-6 | Mobile | Cancel the result | If user select cancel instead of save, it will go to the preview status | Not implemented | N/A
53 | UC-7 | Mobile | Select edit button at detail view | Edit screen of the receipt will be shown | Not implemented | N/A
54 | UC-7 | Mobile | Modify value at edit view and save | Modified value should be applied and it will goto list view | Works as expected | Pass
55 | UC-7 | Mobile | At mobile, go to edit recipt information which is presented at list view of receipt or detail view of receipt | User can edit receipt information manually and after saving it will go to previous state. |  | N/A
56 | UC-7 | Both | After Sync, check the updated information at web app | After sync, updated receipt information can be seen at Web app | Works as exppected | Pass
57 | UC-7 | Web | Edit Receipt, Data editable | Store, Category, Price, Number of items, comment, image of receipt are editable | Not implemented | N/A
58 | UC-7 | Web | Edit Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Not implemented | N/A
59 | UC-7 | Web | Edit Receipt, validation of input values | Editable values are validated where each of values is valid or not | Not implemented | N/A
60 | UC-7 | Web | Edit Receipt, uploading image file of receipt | Allow image type files are allowed to be uploaded and validate less than 2MB file size | Not implemented | N/A
61 | UC-8 | Mobile | Delete one of items and check the list of recipt | User can delete one or more receipt at the receipt list or receipt detail | Works as expected | Pass
62 | UC-8 | Web | Edit Receipt, Clicking 'Delete Receipt' button | pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete receipt and remove relation with related with data and then redirect to 'Receipts' page. When clicking 'Cancel', close pop up window and back to Edit Receipt page | Not implemented | N/A
63 | UC-9 | Both | Search one recipt with keyword at the search menu box | User can search receipt by keywords | Works as expected | Pass
64 | UC-9 | Both | Select a filter at the list | User can filter receipt by store, category, date | Works as expected | Pass
65 | UC-10 | Web | Categories, clicking 'Config-Categories' menu in the navigation bar | Shows user's customizing category data which retrieved from database with pagination | Works as expected | Pass
66 | UC-10 | Web | Categories, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
67 | UC-10 | Web | Categories, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
68 | UC-10 | Web | Categories, Sorted by clicking category name | sorted by category name as descending or ascending | Works as expected | Pass
69 | UC-10 | Web | Categories, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected category | Works as expected | Pass
70 | UC-10 | Web | Categories, Clicking 'Add Category' button | Move to Add Page | Works as expected | Pass
71 | UC-10 | Web | Add Category, input category name | User is allow to input category name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
72 | UC-10 | Web | Add Category, Clicking 'Save Category' button | if category name is valid, 'Save Category' button is enabled, after clicking 'Save Category' button, store new category name into database, and then redirect to 'Categories' page | Works as expected | Pass
73 | UC-10 | Web | Edit Category, 'Delete Category' button is disabled | When category is used by store(s), user is not allowed to delete category, so 'Delete Category' button is disabled | Works as expected | Pass
74 | UC-10 | Web | Edit Category, Edit Category Name | Category Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
75 | UC-10 | Web | Edit Category, Clicking 'Save Category' button | Save category name and redirect to 'Categories' page | Works as expected | Pass
76 | UC-10 | Web | Edit Category, Clicking 'Delete Category' | When clicking enabled 'Delete Category', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete catgory and then redirect to 'Categories' page. When clicking 'Cancel', close the pop up window and back to Edit Category page | Works as expected | Pass
77 | UC-10 | Web | Tags, clicking 'Config-Tags' menu in the navigation bar | Shows user's customizing tag data which retrieved from database with pagination | Works as expected | Pass
78 | UC-10 | Web | Tags, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
79 | UC-10 | Web | Tags, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
80 | UC-10 | Web | Tags, Sorted by clicking category name | sorted by tag name as descending or ascending | Works as expected | Pass
81 | UC-10 | Web | Tags, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected tag | Works as expected | Pass
82 | UC-10 | Web | Tags, Clicking 'Add Tag' button | Move to Add Page | Works as expected | Pass
83 | UC-10 | Web | Add Tag, input tag name | User is allow to input tag name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
84 | UC-10 | Web | Add Tag, Clicking 'Save Tag' button | if tag name is valid, 'Save Tag' button is enabled, after clicking 'Save Tag' button, store new tag name into database, and then redirect to 'Tags' page | Works as expected | Pass
85 | UC-10 | Web | Edit Tag, 'DeleteTag' button is disabled | When tag is used by receipt(s), user is not allowed to delete tag, so 'Delete Tag' button is disabled | Works as expected | Pass
86 | UC-10 | Web | Edit Tag, Edit Tag Name | Tag Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
87 | UC-10 | Web | Edit Tag, Clicking 'Save Tag' button | Save tag name and redirect to 'Tags' page | Works as expected | Pass
88 | UC-10 | Web | Edit Tag, Clicking 'Delete Tag' | When clicking enabled 'Delete Tag', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete tag and then redirect to 'Tags' page. When clicking 'Cancel', close the pop up window and back to Edit Tag page | Works as expected | Pass
89 | UC-10 | Web | Stores, clicking 'Config-Stores' menu in the navigation bar | Shows user's customizing store data which retrieved from database with pagination | Not implemented | N/A
90 | UC-10 | Web | Stores, pagination function | Previous and Next button work correctly, page unit works correctly | Not implemented | N/A
91 | UC-10 | Web | Stores, Search function | When user input value in search text, it filters and show the result in the table correctly | Not implemented | N/A
92 | UC-10 | Web | Stores, Sorted by clicking store name | sorted by store name as descending or ascending | Not implemented | N/A
93 | UC-10 | Web | Stores, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected store | Not implemented | N/A
94 | UC-10 | Web | Stores, Clicking 'Add Store' button | Move to Add Page | Not implemented | N/A
95 | UC-10 | Web | Add Store, input store name | User is allow to input store name and select category, but validate invalid input value such empty value, already existing name, and if category is selected or not | Not implemented | N/A
96 | UC-10 | Web | Add Store, Clicking 'Save Store' button | if store name is valid, 'Save Store' button is enabled, after clicking 'Save Store' button, save new store name with relation to category into database, and then redirect to 'Stores' page | Not implemented | N/A
97 | UC-10 | Web | Edit Store, 'Delete Store' button is disabled | When store is used by receipt(s), user is not allowed to delete store, so 'Delete Store' button is disabled | Not implemented | N/A
98 | UC-10 | Web | Edit Store, Edit Store Name and select category name | Store name is editable and allow to re-select category accordingly, but validate invalid input value such empty value, already existing name, and if category is selected or not | Not implemented | N/A
100 | UC-10 | Web | Edit Store, Clicking 'Save Store' button | Save store name and redirect to 'Stores' page | Not implemented | N/A
101 | UC-10 | Web | Edit Store, Clicking 'Delete Store' | When clicking enabled 'Delete Store', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete store with disconnecting relation to category and then redirect to 'Stores' page. When clicking 'Cancel', close the pop up window and back to Edit Store page | Not implemented | N/A
102 | UC-10 | Both | Select Adding Tag at the receipt list | User can add tag at the list of receipt or detail view of receipt | Works as expected | Pass
103 | UC-10 | Both | Select Addinng Category for the store | There is a menu for adding or modifying store's category | Not implemented | N/A
104 | UC-11 | Web | Chart, Clicking 'chart' menu link in the navigation bar | Move to 'Charts' page and display various type of chars and graphs. Monthly consumption, Comparison bar chart, Tag tendency, Store Amount, Category, Store, Tag, and Tag Progress Bar chart which are all retrived from database | Not implemented | N/A
105 | UC-11 | Web | Chart, Changing the period of month in 'Montly consumption' title bar | Changing all charts and graphs according to selected period of months and display data that retrieve from database | Not implemented | N/A
106 | UC-11 | Web | Chart, Moving mouse on the each value of chart or graph | Pop up the tooltip and show the value of each chart or graph | Not implemented | N/A
107 | UC-11 | Web | Chart, Clicking pdf icon button on the right top of the title bar | Download pdf file as selected chart in Monthly comsumption, Comparison, Tag Tendancy, and Store Amount Charts | Not implemented | N/A
108 | UC-12 | Web | Dashboard, displaying each data | data retrieve from database correctly, if no data in database show no data in it | Not implemented | N/A
109 | UC-12 | Web | Dashboard, chart can export to several types of tiles | Export chart to Print, PDF, JPEG, PNG, SVG files | Not implemented | N/A
110 | UC-12 | Web | Dashboard, edit user's basic profile and change password | User can modify username, firstname, lastname, user potho, and changing password | Not implemented | N/A
111 | UC-12 | Web | Dashboard, upload user's photo in user profile pop-up window | Only allows image type of file and validate less than 2MB file size, if invalid shows message to user | Not implemented | N/A
112 | UC-12 | Web | Dashboard, clicking each of tag name in Tags cloud section | Pop-up window to show receipts list related with selected tag | Not implemented | N/A
113 | UC-12 | Web | Dashboard, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt | Not implemented | N/A
114 | UC-13 | Web | Groups, Clicking 'Groups' on the navigation bar | Move to 'Groups' page | Not implemented | N/A
115 | UC-13 | Web | Groups, showing group information | If user has user's already created group, then display group name as owner. If user has joined group(s) as a member, then display joined group(s) name | Not implemented | N/A
116 | UC-13 | Web | Groups, Clicking 'Add Group' button | When user haven't created a group, 'Add Group' button is visible. After clicking 'Add Group' button, move to 'Add Group' page | Not implemented | N/A
117 | UC-13 | Web | Add Group, input group name, group description | Group name is required and description is optional. Validating group name such as empty value and less than 30 letters. Also description is limited less than 140 letters | Not implemented | N/A
118 | UC-13 | Web | Add Group, Clicking 'Save Group' button | Save group name and descript and redirect to 'Groups' page | Not implemented | N/A
119 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as owner' | Move to eighter of 'Group Receipts', 'View Group', or 'Edit Group' pages | Not implemented | N/A
120 | UC-13 | Web | View Group, show group detailed information | display data from database, and show member(s) email list if the group has member(s). If the loggedin user is an owner of group, shows additional buttons such as 'Edit Group', 'Group Categories', 'Group Stores', and 'Group Tags' | Not implemented | N/A
121 | UC-13 | Web | View Group, clicking each of buttons | move to related pages such as 'Group Receipts', 'Group Charts' | Not implemented | N/A
122 | UC-13 | Web | Edit Group, edit group name, description | Group name and description is editable | Not implemented | N/A
123 | UC-13 | Web | Edit Group, 'Delete Group' is disabled | If group already has member(s), owner is not allowed to delete group, so the 'Delete Group' button is disabled | Not implemented | N/A
124 | UC-13 | Web | Edit Group, Clicking 'Invitation' button | Group owner is allowed to invite user as group member with email, after clicking 'Invitation' button, email is added in the 'Invitation list' | Not implemented | N/A
125 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Invitation list' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Invitation list'. When clicking 'Cancel', close the pop up window and back to Edit Group page | Not implemented | N/A
126 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Leaving Group' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Leaving Group'. The member will not show any more When clicking 'Cancel', close the pop up window and back to Edit Group page | Not implemented | N/A
127 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as member' | Move to relevent page in case of 'Receipt' and 'View Details' | Not implemented | N/A
128 | UC-13 | Web | Groups, Clicking 'Leave Group' font icon button in 'Group as member' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, send request notification to group owner. When clicking 'Cancel', close the pop up window and back to Group page | Not implemented | N/A
129 | UC-13 | Web | Groups, Showing notification | Member can receive notification from group owner's invitation as member | Not implemented | N/A
130 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user | Not implemented | N/A
131 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving | Not implemented | N/A
132 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving | Not implemented | N/A
134 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user | Not implemented | N/A
135 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving | Not implemented | N/A
136 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving | Not implemented | N/A

## Iteration2
Schedule
Planned Start Date |  | Planned End Date |  | Actual Start Date |  | Actual End Date
2016-07-01 |  | 2016-07-04 |  | 2016-07-01 |  | 2016-07-04
SUM
Total TC | Tested TC (Except N/A) | Total Pass |  | Total N/A | Pass Rate
134 | 134 | 84 |  | 47 |  | 62.69%
1 | UC-1 | Both | At login screen, check the availability of sign up menu and check the functionality of sign up menu | There is sign up button or link is available and if user select the button, user can enter their information to sign up |  | Pass
2 | UC-1 | Both | If some required field is unfilled, check the submit button | If user miss some required field at the sign up form, submit button should be inactive At mobile, after user select submit, it will be notified required field is not filled |  | Pass
3 | UC-1 | Both | Filling out sign up form and submit the form | There is a message feedback after user successfully submit the register form. After signing up, user can log in the system automatically |  | Pass
4 | UC-1 | Both | After signup at mobile, try to sign in at web app with the same account | User can login at web app |  | Pass
5 | UC-1 | Web | SignUp page | When user clicks SignUp link, move to SignUp page. User resgister with only email and password | Works as expected | Pass
6 | UC-1 | Web | SignUp, Clicking 'SignUp' button | Email, password input values are validate. Invalid value exist, pop-up message will be showing to notify | Works as expected | Pass
7 | UC-1 | Both | After signup at web app, try to sign in at mobile app with same account | User can login at mobile app |  | Pass
8 | UC-2 | Web | Login, check input validation of email and password | Invalid input values are not allowed and shows message to User | Works as expected | Pass
9 | UC-2 | Web | Login, 'Log In' button is disable | User input valid value at email and password input box then 'Log In' button turns enable to perform login | Works as expected | Pass
10 | UC-2 | Web | Loggedin successfully | redirect to user dashboard page | Works as expected | Pass
11 | UC-2 | Web | Clicking Logout | User access token is delete and redirect to home page (about page) | Works as expected | Pass
12 | UC-3 | Mobile | Exit with autologin checkbox checked, and try to rerun the app | User can login automatically without asking login ID |  | Pass
13 | UC-3 | Mobile | Uncheck the autologin checkbox and exit the app Run the application and check login screen | User login screen should be shown |  | Pass
14 | UC-3 | Mobile | Reinstall the mobile application and try to login with the same account | User can login with the same account |  | Pass
15 | UC-4 | Mobile | After login, check the screen | At initial state , No Receipt screen will be shown After adding receipt, list of receipt will be shown |  | Pass
16 | UC-4 | Mobile | Check the item of list | Receipt information will have date, store, category, total, tag, receipt image, status of sync |  | Pass
17 | UC-4 | Mobile | Select the item of list | If the item of list is selected, detail view of receipt will be shown |  | Pass
18 | UC-4 | Mobile | Long Click on the item of list | Dialog popup will be shown to get confirm to delete the item |  | Pass
19 | UC-4 | Web | Receipts, show user's receipt data | retrieve from receipts data from database with pagination | Works as expected | Pass
20 | UC-4 | Web | Receipts, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
21 | UC-4 | Web | Receipts, Search function | When user input value in search text, it filters and show the result in the table correctly | Not implemented | Pass
22 | UC-4 | Web | Receipts, Sorted by clicking each table title | Except comment, sorted by store name, data, total, number of items out of receipts list | Works as expected | Pass
23 | UC-4 | Web | Receipts, Export Excel file function | When user clicks 'Export Excel' icon, downloading the excel file including contents of table | Works as expected | Pass
24 | UC-5 | Mobile | Check detailed view of receipt | The detailed view will have image of the receipt, store name, date of purchase, category, tag, comment, total, payment method. Edit button will be shown at the bottom |  | Pass
25 | UC-5 | Web | View Receipt, Show data and image of receipt | Display data from database, and show image of photo if attached | Works as expected | Pass
26 | UC-5 | Web | View Receipt, clicking 'Edit button' | Move to Edit Page with related data of the receipt | Works as expected | Pass
27 | UC-5 | Web | View Receipt, clicking 'Tag's button related with the receipt | Pop-up window to show receipts list related with selected tag | Works as expected | Pass
28 | UC-5 | Web | View Receipt, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt | Works as expected | Pass
29 | UC-5 | Web | Unauthorized user trys to access loggedin pages | redirect to the 'Login' pages | Works as expected | Pass
30 | UC-5 | Both | Select one of items for viewing details | At detail, it will show receipt's detail information such as date of purchase, store, category, total, comment, tag, picture of receipt. |  | Pass
31 | UC-6 | Web | Add Receipt, Data editable | Store, Category, Price, Number of items are required and validation check. Comment is optional, but only allowed 140 letters length. Other required input value will be validated, when invalid value exist, pop-up message to notice. | Works as expected | Pass
32 | UC-6 | Web | Add Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Works as expected | Pass
33 | UC-6 | Mobile | At mobile, go to the menu of create receipt | The phone will be in preview state of taking picture |  | Pass
34 | UC-6 | Mobile | Check preview screen | There shoule be some feedback to the user to help taking picture of receipt for better character recognition |  | Pass
35 | UC-6 | Mobile | There's menu to take picture | If user select taking picture, result of character recognition for total and store name will be presented to the user And User can edit the information |  | Pass
36 | UC-6 | Mobile | Save the result | After saving the information, there's feedback it was saved succssfully or not and will be redirected to the list of receipt |  | Pass
37 | UC-6 | Mobile | Scan a receipt for a store listed in the autocomplete | After taking photo, the correct store name is found by OCR. |  | Pass
38 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete | After taking photo, the correct payment method is found by OCR. | Scanning for too few characters produces wrong result | N/A
39 | UC-6 | Mobile | Scan a receipt with a store name not found in the autocomplete | First line of text is suggested as store name |  | N/A
40 | UC-6 | Mobile | Scan a receipt with a store name not found in autocomplete and allow user to add new store name | After taking photo, on Add Receipt screen a store name can be edited and added |  | N/A
41 | UC-6 | Mobile | Scan a receipt and make sure total is found by O.C.R. | The total is found and completed by the O.C.R. | Sometimes subtotal is found by mistake | N/A
42 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete but change it before saving | The user can change a payment method before saving |  | N/A
43 | UC-6 | Mobile | Make sure the image of a receipt is saved after scanning | Bounding boxes are removed from the image | Bounding boxes are still present | N/A
44 | UC-6 | Mobile | During scanning of image before taking photo, display results found so far for user to see | The displayed indicators should be in synchronization with the ocr result |  | N/A
45 | UC-6 | Mobile | Scan a store name printed with stylized text, logo, etc. | O.C.R. should be able to recognize some special fonts, not always but at least some cases should work. |  | N/A
46 | UC-6 | Mobile | Scan a receipt with a date that includes the month fully written out, i.e. "January", "July", etc. | All parts of the date should be found by the O.C.R. |  | N/A
47 | UC-6 | Mobile | Scan a receipt with a date of format dd-mm-yyyy | The O.C.R. should recognize the '-' delimiter and process the date |  | N/A
48 | UC-6 | Mobile | Scan a receipt with a date of format dd/mm/yyyy | The O.C.R. should recognize the '/' delimiter and process the date |  | N/A
49 | UC-6 | Mobile | Scan a receipt with a date that includes three letters of the month written out, i.e. "Jan", "Jul", etc. | The O.C.R. should find the date and scan it correctly |  | Pass
50 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm-dd-yyyy | The O.C.R. should recognize the '-' delimiter and process the date | Works as expected | Pass
51 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm/dd/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Works as expected | Pass
52 | UC-6 | Mobile | Cancel the result | If user select cancel instead of save, it will go to the preview status |  | N/A
53 | UC-7 | Mobile | Select edit button at detail view | Edit screen of the receipt will be shown |  | N/A
54 | UC-7 | Mobile | Modify value at edit view and save | Modified value should be applied and it will goto list view | Works as expected | Pass
55 | UC-7 | Mobile | At mobile, go to edit recipt information which is presented at list view of receipt or detail view of receipt | User can edit receipt information manually and after saving it will go to previous state. |  | N/A
56 | UC-7 | Both | After Sync, check the updated information at web app | After sync, updated receipt information can be seen at Web app | Works as exppected | Pass
57 | UC-7 | Web | Edit Receipt, Data editable | Store, Category, Price, Number of items, comment, image of receipt are editable | Works as expected | Pass
58 | UC-7 | Web | Edit Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Works as expected | Pass
59 | UC-7 | Web | Edit Receipt, validation of input values | Editable values are validated where each of values is valid or not | Works as expected | Pass
60 | UC-7 | Web | Edit Receipt, uploading image file of receipt | Allow image type files are allowed to be uploaded and validate less than 2MB file size | Works as expected | Pass
61 | UC-8 | Mobile | Delete one of items and check the list of recipt | User can delete one or more receipt at the receipt list or receipt detail | Works as expected | Pass
62 | UC-8 | Web | Edit Receipt, Clicking 'Delete Receipt' button | pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete receipt and remove relation with related with data and then redirect to 'Receipts' page. When clicking 'Cancel', close pop up window and back to Edit Receipt page | Works as expected | Pass
63 | UC-9 | Both | Search one recipt with keyword at the search menu box | User can search receipt by keywords | Works as expected | Pass
64 | UC-9 | Both | Select a filter at the list | User can filter receipt by store, category, date | Works as expected | Pass
65 | UC-10 | Web | Categories, clicking 'Config-Categories' menu in the navigation bar | Shows user's customizing category data which retrieved from database with pagination | Works as expected | Pass
66 | UC-10 | Web | Categories, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
67 | UC-10 | Web | Categories, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
68 | UC-10 | Web | Categories, Sorted by clicking category name | sorted by category name as descending or ascending | Works as expected | Pass
69 | UC-10 | Web | Categories, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected category | Works as expected | Pass
70 | UC-10 | Web | Categories, Clicking 'Add Category' button | Move to Add Page | Works as expected | Pass
71 | UC-10 | Web | Add Category, input category name | User is allow to input category name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
72 | UC-10 | Web | Add Category, Clicking 'Save Category' button | if category name is valid, 'Save Category' button is enabled, after clicking 'Save Category' button, store new category name into database, and then redirect to 'Categories' page | Works as expected | Pass
73 | UC-10 | Web | Edit Category, 'Delete Category' button is disabled | When category is used by store(s), user is not allowed to delete category, so 'Delete Category' button is disabled | Works as expected | Pass
74 | UC-10 | Web | Edit Category, Edit Category Name | Category Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
75 | UC-10 | Web | Edit Category, Clicking 'Save Category' button | Save category name and redirect to 'Categories' page | Works as expected | Pass
76 | UC-10 | Web | Edit Category, Clicking 'Delete Category' | When clicking enabled 'Delete Category', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete catgory and then redirect to 'Categories' page. When clicking 'Cancel', close the pop up window and back to Edit Category page | Works as expected | Pass
77 | UC-10 | Web | Tags, clicking 'Config-Tags' menu in the navigation bar | Shows user's customizing tag data which retrieved from database with pagination | Works as expected | Pass
78 | UC-10 | Web | Tags, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
79 | UC-10 | Web | Tags, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
80 | UC-10 | Web | Tags, Sorted by clicking category name | sorted by tag name as descending or ascending | Works as expected | Pass
81 | UC-10 | Web | Tags, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected tag | Works as expected | Pass
82 | UC-10 | Web | Tags, Clicking 'Add Tag' button | Move to Add Page | Works as expected | Pass
83 | UC-10 | Web | Add Tag, input tag name | User is allow to input tag name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
84 | UC-10 | Web | Add Tag, Clicking 'Save Tag' button | if tag name is valid, 'Save Tag' button is enabled, after clicking 'Save Tag' button, store new tag name into database, and then redirect to 'Tags' page | Works as expected | Pass
85 | UC-10 | Web | Edit Tag, 'DeleteTag' button is disabled | When tag is used by receipt(s), user is not allowed to delete tag, so 'Delete Tag' button is disabled | Works as expected | Pass
86 | UC-10 | Web | Edit Tag, Edit Tag Name | Tag Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
87 | UC-10 | Web | Edit Tag, Clicking 'Save Tag' button | Save tag name and redirect to 'Tags' page | Works as expected | Pass
88 | UC-10 | Web | Edit Tag, Clicking 'Delete Tag' | When clicking enabled 'Delete Tag', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete tag and then redirect to 'Tags' page. When clicking 'Cancel', close the pop up window and back to Edit Tag page | Works as expected | Pass
89 | UC-10 | Web | Stores, clicking 'Config-Stores' menu in the navigation bar | Shows user's customizing store data which retrieved from database with pagination | Works as expected | Pass
90 | UC-10 | Web | Stores, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
91 | UC-10 | Web | Stores, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
92 | UC-10 | Web | Stores, Sorted by clicking store name | sorted by store name as descending or ascending | Works as expected | Pass
93 | UC-10 | Web | Stores, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected store | Works as expected | Pass
94 | UC-10 | Web | Stores, Clicking 'Add Store' button | Move to Add Page | Works as expected | Pass
95 | UC-10 | Web | Add Store, input store name | User is allow to input store name and select category, but validate invalid input value such empty value, already existing name, and if category is selected or not | Works as expected | Pass
96 | UC-10 | Web | Add Store, Clicking 'Save Store' button | if store name is valid, 'Save Store' button is enabled, after clicking 'Save Store' button, save new store name with relation to category into database, and then redirect to 'Stores' page | Works as expected | Pass
97 | UC-10 | Web | Edit Store, 'Delete Store' button is disabled | When store is used by receipt(s), user is not allowed to delete store, so 'Delete Store' button is disabled | Works as expected | Pass
98 | UC-10 | Web | Edit Store, Edit Store Name and select category name | Store name is editable and allow to re-select category accordingly, but validate invalid input value such empty value, already existing name, and if category is selected or not | Works as expected | Pass
100 | UC-10 | Web | Edit Store, Clicking 'Save Store' button | Save store name and redirect to 'Stores' page | Works as expected | Pass
101 | UC-10 | Web | Edit Store, Clicking 'Delete Store' | When clicking enabled 'Delete Store', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete store with disconnecting relation to category and then redirect to 'Stores' page. When clicking 'Cancel', close the pop up window and back to Edit Store page | Works as expected | Pass
102 | UC-10 | Both | Select Adding Tag at the receipt list | User can add tag at the list of receipt or detail view of receipt | Works as expected | Pass
103 | UC-10 | Both | Select Addinng Category for the store | There is a menu for adding or modifying store's category | Not implemented | N/A
104 | UC-11 | Web | Chart, Clicking 'chart' menu link in the navigation bar | Move to 'Charts' page and display various type of chars and graphs. Monthly consumption, Comparison bar chart, Tag tendency, Store Amount, Category, Store, Tag, and Tag Progress Bar chart which are all retrived from database | Not implemented | N/A
105 | UC-11 | Web | Chart, Changing the period of month in 'Montly consumption' title bar | Changing all charts and graphs according to selected period of months and display data that retrieve from database | Not implemented | N/A
106 | UC-11 | Web | Chart, Moving mouse on the each value of chart or graph | Pop up the tooltip and show the value of each chart or graph | Not implemented | N/A
107 | UC-11 | Web | Chart, Clicking pdf icon button on the right top of the title bar | Download pdf file as selected chart in Monthly comsumption, Comparison, Tag Tendancy, and Store Amount Charts | Not implemented | N/A
108 | UC-12 | Web | Dashboard, displaying each data | data retrieve from database correctly, if no data in database show no data in it | Not implemented | N/A
109 | UC-12 | Web | Dashboard, chart can export to several types of tiles | Export chart to Print, PDF, JPEG, PNG, SVG files | Not implemented | N/A
110 | UC-12 | Web | Dashboard, edit user's basic profile and change password | User can modify username, firstname, lastname, user potho, and changing password | Not implemented | N/A
111 | UC-12 | Web | Dashboard, upload user's photo in user profile pop-up window | Only allows image type of file and validate less than 2MB file size, if invalid shows message to user | Not implemented | N/A
112 | UC-12 | Web | Dashboard, clicking each of tag name in Tags cloud section | Pop-up window to show receipts list related with selected tag | Not implemented | N/A
113 | UC-12 | Web | Dashboard, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt | Not implemented | N/A
114 | UC-13 | Web | Groups, Clicking 'Groups' on the navigation bar | Move to 'Groups' page | Not implemented | N/A
115 | UC-13 | Web | Groups, showing group information | If user has user's already created group, then display group name as owner. If user has joined group(s) as a member, then display joined group(s) name | Not implemented | N/A
116 | UC-13 | Web | Groups, Clicking 'Add Group' button | When user haven't created a group, 'Add Group' button is visible. After clicking 'Add Group' button, move to 'Add Group' page | Not implemented | N/A
117 | UC-13 | Web | Add Group, input group name, group description | Group name is required and description is optional. Validating group name such as empty value and less than 30 letters. Also description is limited less than 140 letters | Not implemented | N/A
118 | UC-13 | Web | Add Group, Clicking 'Save Group' button | Save group name and descript and redirect to 'Groups' page | Not implemented | N/A
119 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as owner' | Move to eighter of 'Group Receipts', 'View Group', or 'Edit Group' pages | Not implemented | N/A
120 | UC-13 | Web | View Group, show group detailed information | display data from database, and show member(s) email list if the group has member(s). If the loggedin user is an owner of group, shows additional buttons such as 'Edit Group', 'Group Categories', 'Group Stores', and 'Group Tags' | Not implemented | N/A
121 | UC-13 | Web | View Group, clicking each of buttons | move to related pages such as 'Group Receipts', 'Group Charts' | Not implemented | N/A
122 | UC-13 | Web | Edit Group, edit group name, description | Group name and description is editable | Not implemented | N/A
123 | UC-13 | Web | Edit Group, 'Delete Group' is disabled | If group already has member(s), owner is not allowed to delete group, so the 'Delete Group' button is disabled | Not implemented | N/A
124 | UC-13 | Web | Edit Group, Clicking 'Invitation' button | Group owner is allowed to invite user as group member with email, after clicking 'Invitation' button, email is added in the 'Invitation list' | Not implemented | N/A
125 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Invitation list' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Invitation list'. When clicking 'Cancel', close the pop up window and back to Edit Group page | Not implemented | N/A
126 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Leaving Group' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Leaving Group'. The member will not show any more When clicking 'Cancel', close the pop up window and back to Edit Group page | Not implemented | N/A
127 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as member' | Move to relevent page in case of 'Receipt' and 'View Details' | Not implemented | N/A
128 | UC-13 | Web | Groups, Clicking 'Leave Group' font icon button in 'Group as member' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, send request notification to group owner. When clicking 'Cancel', close the pop up window and back to Group page | Not implemented | N/A
129 | UC-13 | Web | Groups, Showing notification | Member can receive notification from group owner's invitation as member | Not implemented | N/A
130 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user | Not implemented | N/A
131 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving | Not implemented | N/A
132 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving | Not implemented | N/A
134 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user | Not implemented | N/A
135 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving | Not implemented | N/A
136 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving | Not implemented | N/A

## Iteration3
Schedule
Planned Start Date |  | Planned End Date |  | Actual Start Date |  | Actual End Date
2016-07-22 |  | 2016-07-25 |  | 2016-07-22 |  | 2016-07-27
SUM
Total TC | Tested TC (Except N/A) | Total Pass | Total N/A | Pass Rate
134 | 20 | 114 | 20 | 85.07%
ID | UseCaseID | Device | Test Case Description | Expected Result | Actual Result Description | Pass/N/A
1 | UC-1 | Both | At login screen, check the availability of sign up menu and check the functionality of sign up menu | There is sign up button or link is available and if user select the button, user can enter their information to sign up |  | Pass
2 | UC-1 | Both | If some required field is unfilled, check the submit button | If user miss some required field at the sign up form, submit button should be inactive At mobile, after user select submit, it will be notified required field is not filled |  | Pass
3 | UC-1 | Both | Filling out sign up form and submit the form | There is a message feedback after user successfully submit the register form. After signing up, user can log in the system automatically |  | Pass
4 | UC-1 | Both | After signup at mobile, try to sign in at web app with the same account | User can login at web app |  | Pass
5 | UC-1 | Web | SignUp page | When user clicks SignUp link, move to SignUp page. User resgister with only email and password | Works as expected | Pass
6 | UC-1 | Web | SignUp, Clicking 'SignUp' button | Email, password input values are validate. Invalid value exist, pop-up message will be showing to notify | Works as expected | Pass
7 | UC-1 | Both | After signup at web app, try to sign in at mobile app with same account | User can login at mobile app |  | Pass
8 | UC-2 | Web | Login, check input validation of email and password | Invalid input values are not allowed and shows message to User | Works as expected | Pass
9 | UC-2 | Web | Login, 'Log In' button is disable | User input valid value at email and password input box then 'Log In' button turns enable to perform login | Works as expected | Pass
10 | UC-2 | Web | Loggedin successfully | redirect to user dashboard page | Works as expected | Pass
11 | UC-2 | Web | Clicking Logout | User access token is delete and redirect to home page (about page) | Works as expected | Pass
12 | UC-3 | Mobile | Exit with autologin checkbox checked, and try to rerun the app | User can login automatically without asking login ID |  | Pass
13 | UC-3 | Mobile | Uncheck the autologin checkbox and exit the app Run the application and check login screen | User login screen should be shown |  | Pass
14 | UC-3 | Mobile | Reinstall the mobile application and try to login with the same account | User can login with the same account |  | Pass
15 | UC-4 | Mobile | After login, check the screen | At initial state , No Receipt screen will be shown After adding receipt, list of receipt will be shown |  | Pass
16 | UC-4 | Mobile | Check the item of list | Receipt information will have date, store, category, total, tag, receipt image, status of sync |  | Pass
17 | UC-4 | Mobile | Select the item of list | If the item of list is selected, detail view of receipt will be shown |  | Pass
18 | UC-4 | Mobile | Long Click on the item of list | Dialog popup will be shown to get confirm to delete the item |  | Pass
19 | UC-4 | Web | Receipts, show user's receipt data | retrieve from receipts data from database with pagination | Works as expected | Pass
20 | UC-4 | Web | Receipts, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
21 | UC-4 | Web | Receipts, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
22 | UC-4 | Web | Receipts, Sorted by clicking each table title | Except comment, sorted by store name, data, total, number of items out of receipts list | Works as expected | Pass
23 | UC-4 | Web | Receipts, Export Excel file function | When user clicks 'Export Excel' icon, downloading the excel file including contents of table | Works as expected | Pass
24 | UC-5 | Mobile | Check detailed view of receipt | The detailed view will have image of the receipt, store name, date of purchase, category, tag, comment, total, payment method. Edit button will be shown at the bottom |  | Pass
25 | UC-5 | Web | View Receipt, Show data and image of receipt | Display data from database, and show image of photo if attached | Works as expected | Pass
26 | UC-5 | Web | View Receipt, clicking 'Edit button' | Move to Edit Page with related data of the receipt | Works as expected | Pass
27 | UC-5 | Web | View Receipt, clicking 'Tag's button related with the receipt | Pop-up window to show receipts list related with selected tag | Works as expected | Pass
28 | UC-5 | Web | View Receipt, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt | Works as expected | Pass
29 | UC-5 | Web | Unauthorized user trys to access loggedin pages | redirect to the 'Login' pages | Works as expected | Pass
30 | UC-5 | Both | Select one of items for viewing details | At detail, it will show receipt's detail information such as date of purchase, store, category, total, comment, tag, picture of receipt. |  | Pass
31 | UC-6 | Web | Add Receipt, Data editable | Store, Category, Price, Number of items are required and validation check. Comment is optional, but only allowed 140 letters length. Other required input value will be validated, when invalid value exist, pop-up message to notice. | Works as expected | Pass
32 | UC-6 | Web | Add Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Works as expected | Pass
33 | UC-6 | Mobile | At mobile, go to the menu of create receipt | The phone will be in preview state of taking picture |  | Pass
34 | UC-6 | Mobile | Check preview screen | There shoule be some feedback to the user to help taking picture of receipt for better character recognition |  | Pass
35 | UC-6 | Mobile | There's menu to take picture | If user select taking picture, result of character recognition for total and store name will be presented to the user And User can edit the information |  | Pass
36 | UC-6 | Mobile | Save the result | After saving the information, there's feedback it was saved succssfully or not and will be redirected to the list of receipt |  | Pass
37 | UC-6 | Mobile | Scan a receipt for a store listed in the autocomplete | After taking photo, the correct store name is found by OCR. |  | Pass
38 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete | After taking photo, the correct payment method is found by OCR. | Scanning for too few characters produces wrong result | Pass
39 | UC-6 | Mobile | Scan a receipt with a store name not found in the autocomplete | First line of text is suggested as store name |  | Pass
40 | UC-6 | Mobile | Scan a receipt with a store name not found in autocomplete and allow user to add new store name | After taking photo, on Add Receipt screen a store name can be edited and added |  | N/A
41 | UC-6 | Mobile | Scan a receipt and make sure total is found by O.C.R. | The total is found and completed by the O.C.R. | Sometimes subtotal is found by mistake | N/A
42 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete but change it before saving | The user can change a payment method before saving |  | N/A
43 | UC-6 | Mobile | Make sure the image of a receipt is saved after scanning | Bounding boxes are removed from the image | Bounding boxes are still present | Pass
44 | UC-6 | Mobile | During scanning of image before taking photo, display results found so far for user to see | The displayed indicators should be in synchronization with the ocr result |  | N/A
45 | UC-6 | Mobile | Scan a store name printed with stylized text, logo, etc. | O.C.R. should be able to recognize some special fonts, not always but at least some cases should work. |  | N/A
46 | UC-6 | Mobile | Scan a receipt with a date that includes the month fully written out, i.e. "January", "July", etc. | All parts of the date should be found by the O.C.R. |  | N/A
47 | UC-6 | Mobile | Scan a receipt with a date of format dd-mm-yyyy | The O.C.R. should recognize the '-' delimiter and process the date |  | Pass
48 | UC-6 | Mobile | Scan a receipt with a date of format dd/mm/yyyy | The O.C.R. should recognize the '/' delimiter and process the date |  | Pass
49 | UC-6 | Mobile | Scan a receipt with a date that includes three letters of the month written out, i.e. "Jan", "Jul", etc. | The O.C.R. should find the date and scan it correctly |  | Pass
50 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm-dd-yyyy | The O.C.R. should recognize the '-' delimiter and process the date | Works as expected | Pass
51 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm/dd/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Works as expected | Pass
52 | UC-6 | Mobile | Cancel the result | If user select cancel instead of save, it will go to the preview status |  | N/A
53 | UC-7 | Mobile | Select edit button at detail view | Edit screen of the receipt will be shown |  | N/A
54 | UC-7 | Mobile | Modify value at edit view and save | Modified value should be applied and it will goto list view | Works as expected | Pass
55 | UC-7 | Mobile | At mobile, go to edit recipt information which is presented at list view of receipt or detail view of receipt | User can edit receipt information manually and after saving it will go to previous state. |  | N/A
56 | UC-7 | Both | After Sync, check the updated information at web app | After sync, updated receipt information can be seen at Web app | Works as exppected | Pass
57 | UC-7 | Web | Edit Receipt, Data editable | Store, Category, Price, Number of items, comment, image of receipt are editable | Works as expected | Pass
58 | UC-7 | Web | Edit Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Works as expected | Pass
59 | UC-7 | Web | Edit Receipt, validation of input values | Editable values are validated where each of values is valid or not | Works as expected | Pass
60 | UC-7 | Web | Edit Receipt, uploading image file of receipt | Allow image type files are allowed to be uploaded and validate less than 2MB file size | Works as expected | Pass
61 | UC-8 | Mobile | Delete one of items and check the list of recipt | User can delete one or more receipt at the receipt list or receipt detail | Works as expected | Pass
62 | UC-8 | Web | Edit Receipt, Clicking 'Delete Receipt' button | pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete receipt and remove relation with related with data and then redirect to 'Receipts' page. When clicking 'Cancel', close pop up window and back to Edit Receipt page | Works as expected | Pass
63 | UC-9 | Both | Search one recipt with keyword at the search menu box | User can search receipt by keywords | Works as expected | Pass
64 | UC-9 | Both | Select a filter at the list | User can filter receipt by store, category, date | Works as expected | Pass
65 | UC-10 | Web | Categories, clicking 'Config-Categories' menu in the navigation bar | Shows user's customizing category data which retrieved from database with pagination | Works as expected | Pass
66 | UC-10 | Web | Categories, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
67 | UC-10 | Web | Categories, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
68 | UC-10 | Web | Categories, Sorted by clicking category name | sorted by category name as descending or ascending | Works as expected | Pass
69 | UC-10 | Web | Categories, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected category | Works as expected | Pass
70 | UC-10 | Web | Categories, Clicking 'Add Category' button | Move to Add Page | Works as expected | Pass
71 | UC-10 | Web | Add Category, input category name | User is allow to input category name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
72 | UC-10 | Web | Add Category, Clicking 'Save Category' button | if category name is valid, 'Save Category' button is enabled, after clicking 'Save Category' button, store new category name into database, and then redirect to 'Categories' page | Works as expected | Pass
73 | UC-10 | Web | Edit Category, 'Delete Category' button is disabled | When category is used by store(s), user is not allowed to delete category, so 'Delete Category' button is disabled | Works as expected | Pass
74 | UC-10 | Web | Edit Category, Edit Category Name | Category Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
75 | UC-10 | Web | Edit Category, Clicking 'Save Category' button | Save category name and redirect to 'Categories' page | Works as expected | Pass
76 | UC-10 | Web | Edit Category, Clicking 'Delete Category' | When clicking enabled 'Delete Category', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete catgory and then redirect to 'Categories' page. When clicking 'Cancel', close the pop up window and back to Edit Category page | Works as expected | Pass
77 | UC-10 | Web | Tags, clicking 'Config-Tags' menu in the navigation bar | Shows user's customizing tag data which retrieved from database with pagination | Works as expected | Pass
78 | UC-10 | Web | Tags, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
79 | UC-10 | Web | Tags, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
80 | UC-10 | Web | Tags, Sorted by clicking category name | sorted by tag name as descending or ascending | Works as expected | Pass
81 | UC-10 | Web | Tags, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected tag | Works as expected | Pass
82 | UC-10 | Web | Tags, Clicking 'Add Tag' button | Move to Add Page | Works as expected | Pass
83 | UC-10 | Web | Add Tag, input tag name | User is allow to input tag name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
84 | UC-10 | Web | Add Tag, Clicking 'Save Tag' button | if tag name is valid, 'Save Tag' button is enabled, after clicking 'Save Tag' button, store new tag name into database, and then redirect to 'Tags' page | Works as expected | Pass
85 | UC-10 | Web | Edit Tag, 'DeleteTag' button is disabled | When tag is used by receipt(s), user is not allowed to delete tag, so 'Delete Tag' button is disabled | Works as expected | Pass
86 | UC-10 | Web | Edit Tag, Edit Tag Name | Tag Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
87 | UC-10 | Web | Edit Tag, Clicking 'Save Tag' button | Save tag name and redirect to 'Tags' page | Works as expected | Pass
88 | UC-10 | Web | Edit Tag, Clicking 'Delete Tag' | When clicking enabled 'Delete Tag', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete tag and then redirect to 'Tags' page. When clicking 'Cancel', close the pop up window and back to Edit Tag page | Works as expected | Pass
89 | UC-10 | Web | Stores, clicking 'Config-Stores' menu in the navigation bar | Shows user's customizing store data which retrieved from database with pagination | Works as expected | Pass
90 | UC-10 | Web | Stores, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
91 | UC-10 | Web | Stores, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
92 | UC-10 | Web | Stores, Sorted by clicking store name | sorted by store name as descending or ascending | Works as expected | Pass
93 | UC-10 | Web | Stores, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected store | Works as expected | Pass
94 | UC-10 | Web | Stores, Clicking 'Add Store' button | Move to Add Page | Works as expected | Pass
95 | UC-10 | Web | Add Store, input store name | User is allow to input store name and select category, but validate invalid input value such empty value, already existing name, and if category is selected or not | Works as expected | Pass
96 | UC-10 | Web | Add Store, Clicking 'Save Store' button | if store name is valid, 'Save Store' button is enabled, after clicking 'Save Store' button, save new store name with relation to category into database, and then redirect to 'Stores' page | Works as expected | Pass
97 | UC-10 | Web | Edit Store, 'Delete Store' button is disabled | When store is used by receipt(s), user is not allowed to delete store, so 'Delete Store' button is disabled | Works as expected | Pass
98 | UC-10 | Web | Edit Store, Edit Store Name and select category name | Store name is editable and allow to re-select category accordingly, but validate invalid input value such empty value, already existing name, and if category is selected or not | Works as expected | Pass
100 | UC-10 | Web | Edit Store, Clicking 'Save Store' button | Save store name and redirect to 'Stores' page | Works as expected | Pass
101 | UC-10 | Web | Edit Store, Clicking 'Delete Store' | When clicking enabled 'Delete Store', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete store with disconnecting relation to category and then redirect to 'Stores' page. When clicking 'Cancel', close the pop up window and back to Edit Store page | Works as expected | Pass
102 | UC-10 | Both | Select Adding Tag at the receipt list | User can add tag at the list of receipt or detail view of receipt | Works as expected | Pass
103 | UC-10 | Both | Select Addinng Category for the store | There is a menu for adding or modifying store's category | Not implemented | N/A
104 | UC-11 | Web | Chart, Clicking 'chart' menu link in the navigation bar | Move to 'Charts' page and display various type of chars and graphs. Monthly consumption, Comparison bar chart, Tag tendency, Store Amount, Category, Store, Tag, and Tag Progress Bar chart which are all retrived from database | Not implemented | N/A
105 | UC-11 | Web | Chart, Changing the period of month in 'Montly consumption' title bar | Changing all charts and graphs according to selected period of months and display data that retrieve from database | Not implemented | N/A
106 | UC-11 | Web | Chart, Moving mouse on the each value of chart or graph | Pop up the tooltip and show the value of each chart or graph | Not implemented | N/A
107 | UC-11 | Web | Chart, Clicking pdf icon button on the right top of the title bar | Download pdf file as selected chart in Monthly comsumption, Comparison, Tag Tendancy, and Store Amount Charts | Not implemented | N/A
108 | UC-12 | Web | Dashboard, displaying each data | data retrieve from database correctly, if no data in database show no data in it | Not implemented | N/A
109 | UC-12 | Web | Dashboard, chart can export to several types of tiles | Export chart to Print, PDF, JPEG, PNG, SVG files | Not implemented | N/A
110 | UC-12 | Web | Dashboard, edit user's basic profile and change password | User can modify username, firstname, lastname, user potho, and changing password | Not implemented | N/A
111 | UC-12 | Web | Dashboard, upload user's photo in user profile pop-up window | Only allows image type of file and validate less than 2MB file size, if invalid shows message to user | Not implemented | N/A
112 | UC-12 | Web | Dashboard, clicking each of tag name in Tags cloud section | Pop-up window to show receipts list related with selected tag | Not implemented | N/A
113 | UC-12 | Web | Dashboard, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt | Not implemented | N/A
114 | UC-13 | Web | Groups, Clicking 'Groups' on the navigation bar | Move to 'Groups' page | Works as expected | Pass
115 | UC-13 | Web | Groups, showing group information | If user has user's already created group, then display group name as owner. If user has joined group(s) as a member, then display joined group(s) name | Works as expected | Pass
116 | UC-13 | Web | Groups, Clicking 'Add Group' button | When user haven't created a group, 'Add Group' button is visible. After clicking 'Add Group' button, move to 'Add Group' page | Works as expected | Pass
117 | UC-13 | Web | Add Group, input group name, group description | Group name is required and description is optional. Validating group name such as empty value and less than 30 letters. Also description is limited less than 140 letters | Works as expected | Pass
118 | UC-13 | Web | Add Group, Clicking 'Save Group' button | Save group name and descript and redirect to 'Groups' page | Works as expected | Pass
119 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as owner' | Move to eighter of 'Group Receipts', 'View Group', or 'Edit Group' pages | Works as expected | Pass
120 | UC-13 | Web | View Group, show group detailed information | display data from database, and show member(s) email list if the group has member(s). If the loggedin user is an owner of group, shows additional buttons such as 'Edit Group', 'Group Categories', 'Group Stores', and 'Group Tags' | Works as expected | Pass
121 | UC-13 | Web | View Group, clicking each of buttons | move to related pages such as 'Group Receipts', 'Group Charts' | Works as expected | Pass
122 | UC-13 | Web | Edit Group, edit group name, description | Group name and description is editable | Works as expected | Pass
123 | UC-13 | Web | Edit Group, 'Delete Group' is disabled | If group already has member(s), owner is not allowed to delete group, so the 'Delete Group' button is disabled | Works as expected | Pass
124 | UC-13 | Web | Edit Group, Clicking 'Invitation' button | Group owner is allowed to invite user as group member with email, after clicking 'Invitation' button, email is added in the 'Invitation list' | Works as expected | Pass
125 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Invitation list' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Invitation list'. When clicking 'Cancel', close the pop up window and back to Edit Group page | Works as expected | Pass
126 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Leaving Group' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Leaving Group'. The member will not show any more When clicking 'Cancel', close the pop up window and back to Edit Group page | Works as expected | Pass
127 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as member' | Move to relevent page in case of 'Receipt' and 'View Details' | Works as expected | Pass
128 | UC-13 | Web | Groups, Clicking 'Leave Group' font icon button in 'Group as member' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, send request notification to group owner. When clicking 'Cancel', close the pop up window and back to Group page | Works as expected | Pass
129 | UC-13 | Web | Groups, Showing notification | Member can receive notification from group owner's invitation as member | Works as expected | Pass
130 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user | Works as expected | Pass
131 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving | Works as expected | Pass
132 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving | Works as expected | Pass
134 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user | Works as expected | Pass
135 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving | Works as expected | Pass
136 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving | Works as expected | Pass

## Iteration4
Schedule
Planned Start Date |  | Planned End Date |  | Actual Start Date |  | Actual End Date
2016-08-01 |  | 2016-08-04 |  | 2018-08-01 |  | 2016-08-10
SUM
Total TC | Tested TC (Except N/A) | Total Pass |  | Total N/A | Pass Rate
134 | 1 | 133 |  | 1 | 99.25%
ID | UseCaseID | Device | Test Case Description | Expected Result | Actual Result Description | Pass/N/A
1 | UC-1 | Both | At login screen, check the availability of sign up menu and check the functionality of sign up menu | There is sign up button or link is available and if user select the button, user can enter their information to sign up |  | Pass
2 | UC-1 | Both | If some required field is unfilled, check the submit button | If user miss some required field at the sign up form, submit button should be inactive At mobile, after user select submit, it will be notified required field is not filled |  | Pass
3 | UC-1 | Both | Filling out sign up form and submit the form | There is a message feedback after user successfully submit the register form. After signing up, user can log in the system automatically |  | Pass
4 | UC-1 | Both | After signup at mobile, try to sign in at web app with the same account | User can login at web app |  | Pass
5 | UC-1 | Web | SignUp page | When user clicks SignUp link, move to SignUp page. User resgister with only email and password | Works as expected | Pass
6 | UC-1 | Web | SignUp, Clicking 'SignUp' button | Email, password input values are validate. Invalid value exist, pop-up message will be showing to notify | Works as expected | Pass
7 | UC-1 | Both | After signup at web app, try to sign in at mobile app with same account | User can login at mobile app |  | Pass
8 | UC-2 | Web | Login, check input validation of email and password | Invalid input values are not allowed and shows message to User | Works as expected | Pass
9 | UC-2 | Web | Login, 'Log In' button is disable | User input valid value at email and password input box then 'Log In' button turns enable to perform login | Works as expected | Pass
10 | UC-2 | Web | Loggedin successfully | redirect to user dashboard page | Works as expected | Pass
11 | UC-2 | Web | Clicking Logout | User access token is delete and redirect to home page (about page) | Works as expected | Pass
12 | UC-3 | Mobile | Exit with autologin checkbox checked, and try to rerun the app | User can login automatically without asking login ID |  | Pass
13 | UC-3 | Mobile | Uncheck the autologin checkbox and exit the app Run the application and check login screen | User login screen should be shown |  | Pass
14 | UC-3 | Mobile | Reinstall the mobile application and try to login with the same account | User can login with the same account |  | Pass
15 | UC-4 | Mobile | After login, check the screen | At initial state , No Receipt screen will be shown After adding receipt, list of receipt will be shown |  | Pass
16 | UC-4 | Mobile | Check the item of list | Receipt information will have date, store, category, total, tag, receipt image, status of sync |  | Pass
17 | UC-4 | Mobile | Select the item of list | If the item of list is selected, detail view of receipt will be shown |  | Pass
18 | UC-4 | Mobile | Long Click on the item of list | Dialog popup will be shown to get confirm to delete the item |  | Pass
19 | UC-4 | Web | Receipts, show user's receipt data | retrieve from receipts data from database with pagination | Works as expected | Pass
20 | UC-4 | Web | Receipts, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
21 | UC-4 | Web | Receipts, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
22 | UC-4 | Web | Receipts, Sorted by clicking each table title | Except comment, sorted by store name, data, total, number of items out of receipts list | Works as expected | Pass
23 | UC-4 | Web | Receipts, Export Excel file function | When user clicks 'Export Excel' icon, downloading the excel file including contents of table | Works as expected | Pass
24 | UC-5 | Mobile | Check detailed view of receipt | The detailed view will have image of the receipt, store name, date of purchase, category, tag, comment, total, payment method. Edit button will be shown at the bottom |  | Pass
25 | UC-5 | Web | View Receipt, Show data and image of receipt | Display data from database, and show image of photo if attached | Works as expected | Pass
26 | UC-5 | Web | View Receipt, clicking 'Edit button' | Move to Edit Page with related data of the receipt | Works as expected | Pass
27 | UC-5 | Web | View Receipt, clicking 'Tag's button related with the receipt | Pop-up window to show receipts list related with selected tag | Works as expected | Pass
28 | UC-5 | Web | View Receipt, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt | Works as expected | Pass
29 | UC-5 | Web | Unauthorized user trys to access loggedin pages | redirect to the 'Login' pages | Works as expected | Pass
30 | UC-5 | Both | Select one of items for viewing details | At detail, it will show receipt's detail information such as date of purchase, store, category, total, comment, tag, picture of receipt. |  | Pass
31 | UC-6 | Web | Add Receipt, Data editable | Store, Category, Price, Number of items are required and validation check. Comment is optional, but only allowed 140 letters length. Other required input value will be validated, when invalid value exist, pop-up message to notice. | Works as expected | Pass
32 | UC-6 | Web | Add Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Works as expected | Pass
33 | UC-6 | Mobile | At mobile, go to the menu of create receipt | The phone will be in preview state of taking picture |  | Pass
34 | UC-6 | Mobile | Check preview screen | There shoule be some feedback to the user to help taking picture of receipt for better character recognition |  | Pass
35 | UC-6 | Mobile | There's menu to take picture | If user select taking picture, result of character recognition for total and store name will be presented to the user And User can edit the information |  | Pass
36 | UC-6 | Mobile | Save the result | After saving the information, there's feedback it was saved succssfully or not and will be redirected to the list of receipt |  | Pass
37 | UC-6 | Mobile | Scan a receipt for a store listed in the autocomplete | After taking photo, the correct store name is found by OCR. |  | Pass
38 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete | After taking photo, the correct payment method is found by OCR. |  | Pass
39 | UC-6 | Mobile | Scan a receipt with a store name not found in the autocomplete | First line of text is suggested as store name |  | Pass
40 | UC-6 | Mobile | Scan a receipt with a store name not found in autocomplete and allow user to add new store name | After taking photo, on Add Receipt screen a store name can be edited and added |  | Pass
41 | UC-6 | Mobile | Scan a receipt and make sure total is found by O.C.R. | The total is found and completed by the O.C.R. |  | Pass
42 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete but change it before saving | The user can change a payment method before saving | Tested with Visa successfully | Pass
43 | UC-6 | Mobile | Make sure the image of a receipt is saved after scanning | Bounding boxes are removed from the image |  | Pass
44 | UC-6 | Mobile | During scanning of image before taking photo, display results found so far for user to see | The displayed indicators should be in synchronization with the ocr result |  | Pass
45 | UC-6 | Mobile | Scan a store name printed with stylized text, logo, etc. | O.C.R. should be able to recognize some special fonts, not always but at least some cases should work. |  | Pass
46 | UC-6 | Mobile | Scan a receipt with a date that includes the month fully written out, i.e. "January", "July", etc. | All parts of the date should be found by the O.C.R. |  | Pass
47 | UC-6 | Mobile | Scan a receipt with a date of format dd-mm-yyyy | The O.C.R. should recognize the '-' delimiter and process the date |  | Pass
48 | UC-6 | Mobile | Scan a receipt with a date of format dd/mm/yyyy | The O.C.R. should recognize the '/' delimiter and process the date |  | Pass
49 | UC-6 | Mobile | Scan a receipt with a date that includes three letters of the month written out, i.e. "Jan", "Jul", etc. | The O.C.R. should find the date and scan it correctly |  | Pass
50 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm-dd-yyyy | The O.C.R. should recognize the '-' delimiter and process the date | Works as expected | Pass
51 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm/dd/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Works as expected | Pass
52 | UC-6 | Mobile | Cancel the result | If user select cancel instead of save, it will go to the preview status |  | Pass
53 | UC-7 | Mobile | Select edit button at detail view | Edit screen of the receipt will be shown |  | Pass
54 | UC-7 | Mobile | Modify value at edit view and save | Modified value should be applied and it will goto list view | Works as expected | Pass
55 | UC-7 | Mobile | At mobile, go to edit recipt information which is presented at list view of receipt or detail view of receipt | User can edit receipt information manually and after saving it will go to previous state. |  | Pass
56 | UC-7 | Both | After Sync, check the updated information at web app | After sync, updated receipt information can be seen at Web app | Works as exppected | Pass
57 | UC-7 | Web | Edit Receipt, Data editable | Store, Category, Price, Number of items, comment, image of receipt are editable | Works as expected | Pass
58 | UC-7 | Web | Edit Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Works as expected | Pass
59 | UC-7 | Web | Edit Receipt, validation of input values | Editable values are validated where each of values is valid or not | Works as expected | Pass
60 | UC-7 | Web | Edit Receipt, uploading image file of receipt | Allow image type files are allowed to be uploaded and validate less than 2MB file size | Works as expected | Pass
61 | UC-8 | Mobile | Delete one of items and check the list of recipt | User can delete one or more receipt at the receipt list or receipt detail | Works as expected | Pass
62 | UC-8 | Web | Edit Receipt, Clicking 'Delete Receipt' button | pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete receipt and remove relation with related with data and then redirect to 'Receipts' page. When clicking 'Cancel', close pop up window and back to Edit Receipt page | Works as expected | Pass
63 | UC-9 | Both | Search one recipt with keyword at the search menu box | User can search receipt by keywords | Works as expected | Pass
64 | UC-9 | Both | Select a filter at the list | User can filter receipt by store, category, date | Works as expected | Pass
65 | UC-10 | Web | Categories, clicking 'Config-Categories' menu in the navigation bar | Shows user's customizing category data which retrieved from database with pagination | Works as expected | Pass
66 | UC-10 | Web | Categories, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
67 | UC-10 | Web | Categories, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
68 | UC-10 | Web | Categories, Sorted by clicking category name | sorted by category name as descending or ascending | Works as expected | Pass
69 | UC-10 | Web | Categories, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected category | Works as expected | Pass
70 | UC-10 | Web | Categories, Clicking 'Add Category' button | Move to Add Page | Works as expected | Pass
71 | UC-10 | Web | Add Category, input category name | User is allow to input category name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
72 | UC-10 | Web | Add Category, Clicking 'Save Category' button | if category name is valid, 'Save Category' button is enabled, after clicking 'Save Category' button, store new category name into database, and then redirect to 'Categories' page | Works as expected | Pass
73 | UC-10 | Web | Edit Category, 'Delete Category' button is disabled | When category is used by store(s), user is not allowed to delete category, so 'Delete Category' button is disabled | Works as expected | Pass
74 | UC-10 | Web | Edit Category, Edit Category Name | Category Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
75 | UC-10 | Web | Edit Category, Clicking 'Save Category' button | Save category name and redirect to 'Categories' page | Works as expected | Pass
76 | UC-10 | Web | Edit Category, Clicking 'Delete Category' | When clicking enabled 'Delete Category', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete catgory and then redirect to 'Categories' page. When clicking 'Cancel', close the pop up window and back to Edit Category page | Works as expected | Pass
77 | UC-10 | Web | Tags, clicking 'Config-Tags' menu in the navigation bar | Shows user's customizing tag data which retrieved from database with pagination | Works as expected | Pass
78 | UC-10 | Web | Tags, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
79 | UC-10 | Web | Tags, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
80 | UC-10 | Web | Tags, Sorted by clicking category name | sorted by tag name as descending or ascending | Works as expected | Pass
81 | UC-10 | Web | Tags, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected tag | Works as expected | Pass
82 | UC-10 | Web | Tags, Clicking 'Add Tag' button | Move to Add Page | Works as expected | Pass
83 | UC-10 | Web | Add Tag, input tag name | User is allow to input tag name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
84 | UC-10 | Web | Add Tag, Clicking 'Save Tag' button | if tag name is valid, 'Save Tag' button is enabled, after clicking 'Save Tag' button, store new tag name into database, and then redirect to 'Tags' page | Works as expected | Pass
85 | UC-10 | Web | Edit Tag, 'DeleteTag' button is disabled | When tag is used by receipt(s), user is not allowed to delete tag, so 'Delete Tag' button is disabled | Works as expected | Pass
86 | UC-10 | Web | Edit Tag, Edit Tag Name | Tag Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
87 | UC-10 | Web | Edit Tag, Clicking 'Save Tag' button | Save tag name and redirect to 'Tags' page | Works as expected | Pass
88 | UC-10 | Web | Edit Tag, Clicking 'Delete Tag' | When clicking enabled 'Delete Tag', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete tag and then redirect to 'Tags' page. When clicking 'Cancel', close the pop up window and back to Edit Tag page | Works as expected | Pass
89 | UC-10 | Web | Stores, clicking 'Config-Stores' menu in the navigation bar | Shows user's customizing store data which retrieved from database with pagination | Works as expected | Pass
90 | UC-10 | Web | Stores, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
91 | UC-10 | Web | Stores, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
92 | UC-10 | Web | Stores, Sorted by clicking store name | sorted by store name as descending or ascending | Works as expected | Pass
93 | UC-10 | Web | Stores, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected store | Works as expected | Pass
94 | UC-10 | Web | Stores, Clicking 'Add Store' button | Move to Add Page | Works as expected | Pass
95 | UC-10 | Web | Add Store, input store name | User is allow to input store name and select category, but validate invalid input value such empty value, already existing name, and if category is selected or not | Works as expected | Pass
96 | UC-10 | Web | Add Store, Clicking 'Save Store' button | if store name is valid, 'Save Store' button is enabled, after clicking 'Save Store' button, save new store name with relation to category into database, and then redirect to 'Stores' page | Works as expected | Pass
97 | UC-10 | Web | Edit Store, 'Delete Store' button is disabled | When store is used by receipt(s), user is not allowed to delete store, so 'Delete Store' button is disabled | Works as expected | Pass
98 | UC-10 | Web | Edit Store, Edit Store Name and select category name | Store name is editable and allow to re-select category accordingly, but validate invalid input value such empty value, already existing name, and if category is selected or not | Works as expected | Pass
100 | UC-10 | Web | Edit Store, Clicking 'Save Store' button | Save store name and redirect to 'Stores' page | Works as expected | Pass
101 | UC-10 | Web | Edit Store, Clicking 'Delete Store' | When clicking enabled 'Delete Store', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete store with disconnecting relation to category and then redirect to 'Stores' page. When clicking 'Cancel', close the pop up window and back to Edit Store page | Works as expected | Pass
102 | UC-10 | Both | Select Adding Tag at the receipt list | User can add tag at the list of receipt or detail view of receipt | Works as expected | Pass | Yes
103 | UC-10 | Both | Select Addinng Category for the store | There is a menu for adding or modifying store's category | Not implemented | N/A | No
104 | UC-11 | Web | Chart, Clicking 'chart' menu link in the navigation bar | Move to 'Charts' page and display various type of chars and graphs. Monthly consumption, Comparison bar chart, Tag tendency, Store Amount, Category, Store, Tag, and Tag Progress Bar chart which are all retrived from database | Works as expected | Pass
105 | UC-11 | Web | Chart, Changing the period of month in 'Montly consumption' title bar | Changing all charts and graphs according to selected period of months and display data that retrieve from database | Works as expected | Pass
106 | UC-11 | Web | Chart, Moving mouse on the each value of chart or graph | Pop up the tooltip and show the value of each chart or graph | Works as expected | Pass
107 | UC-11 | Web | Chart, Clicking pdf icon button on the right top of the title bar | Download pdf file as selected chart in Monthly comsumption, Comparison, Tag Tendancy, and Store Amount Charts | Works as expected | Pass
108 | UC-12 | Web | Dashboard, displaying each data | data retrieve from database correctly, if no data in database show no data in it | Works as expected | Pass
109 | UC-12 | Web | Dashboard, chart can export to several types of tiles | Export chart to Print, PDF, JPEG, PNG, SVG files | Works as expected | Pass
110 | UC-12 | Web | Dashboard, edit user's basic profile and change password | User can modify username, firstname, lastname, user potho, and changing password | Works as expected | Pass
111 | UC-12 | Web | Dashboard, upload user's photo in user profile pop-up window | Only allows image type of file and validate less than 2MB file size, if invalid shows message to user | Works as expected | Pass
112 | UC-12 | Web | Dashboard, clicking each of tag name in Tags cloud section | Pop-up window to show receipts list related with selected tag | Works as expected | Pass
113 | UC-12 | Web | Dashboard, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt | Works as expected | Pass
114 | UC-13 | Web | Groups, Clicking 'Groups' on the navigation bar | Move to 'Groups' page | Works as expected | Pass
115 | UC-13 | Web | Groups, showing group information | If user has user's already created group, then display group name as owner. If user has joined group(s) as a member, then display joined group(s) name | Works as expected | Pass
116 | UC-13 | Web | Groups, Clicking 'Add Group' button | When user haven't created a group, 'Add Group' button is visible. After clicking 'Add Group' button, move to 'Add Group' page | Works as expected | Pass
117 | UC-13 | Web | Add Group, input group name, group description | Group name is required and description is optional. Validating group name such as empty value and less than 30 letters. Also description is limited less than 140 letters | Works as expected | Pass
118 | UC-13 | Web | Add Group, Clicking 'Save Group' button | Save group name and descript and redirect to 'Groups' page | Works as expected | Pass
119 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as owner' | Move to eighter of 'Group Receipts', 'View Group', or 'Edit Group' pages | Works as expected | Pass
120 | UC-13 | Web | View Group, show group detailed information | display data from database, and show member(s) email list if the group has member(s). If the loggedin user is an owner of group, shows additional buttons such as 'Edit Group', 'Group Categories', 'Group Stores', and 'Group Tags' | Works as expected | Pass
121 | UC-13 | Web | View Group, clicking each of buttons | move to related pages such as 'Group Receipts', 'Group Charts' | Works as expected | Pass
122 | UC-13 | Web | Edit Group, edit group name, description | Group name and description is editable | Works as expected | Pass
123 | UC-13 | Web | Edit Group, 'Delete Group' is disabled | If group already has member(s), owner is not allowed to delete group, so the 'Delete Group' button is disabled | Works as expected | Pass
124 | UC-13 | Web | Edit Group, Clicking 'Invitation' button | Group owner is allowed to invite user as group member with email, after clicking 'Invitation' button, email is added in the 'Invitation list' | Works as expected | Pass
125 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Invitation list' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Invitation list'. When clicking 'Cancel', close the pop up window and back to Edit Group page | Works as expected | Pass
126 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Leaving Group' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Leaving Group'. The member will not show any more When clicking 'Cancel', close the pop up window and back to Edit Group page | Works as expected | Pass
127 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as member' | Move to relevent page in case of 'Receipt' and 'View Details' | Works as expected | Pass
128 | UC-13 | Web | Groups, Clicking 'Leave Group' font icon button in 'Group as member' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, send request notification to group owner. When clicking 'Cancel', close the pop up window and back to Group page | Works as expected | Pass
129 | UC-13 | Web | Groups, Showing notification | Member can receive notification from group owner's invitation as member | Works as expected | Pass
130 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user | Works as expected | Pass
131 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving | Works as expected | Pass
132 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving | Works as expected | Pass
134 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user | Works as expected | Pass
135 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving | Works as expected | Pass
136 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving | Works as expected | Pass