## Testcases
Last Modifed | 2016-08-09
ID | UseCaseID | Device | Test Case Description | Expected Result
1 | UC-1 | Both | At login screen, check the availability of sign up menu and check the functionality of sign up menu | There is sign up button or link is available and if user select the button, user can enter their information to sign up
2 | UC-1 | Both | If some required field is unfilled, check the submit button | If user miss some required field at the sign up form, submit button should be inactive At mobile, after user select submit, it will be notified required field is not filled
3 | UC-1 | Both | Filling out sign up form and submit the form | There is a message feedback after user successfully submit the register form. After signing up, user can log in the system automatically
4 | UC-1 | Both | After signup at mobile, try to sign in at web app with the same account | User can login at web app
5 | UC-1 | Both | After signup at web app, try to sign in at mobile app with same account | User can login at mobile app
6 | UC-2 | Both | Check functionality of login | User can login with registered email id
7 | UC-2 | Mobile | Check the existence of auto login checkbox | At login form screen, auto login check box should exist
8 | UC-3 | Mobile | If user check auto login checkbox, try to login and Check setting menu | After login successfully, autologin checkbox should be checked
9 | UC-3 | Mobile | Exit with autologin checkbox checked, and try to rerun the app | User can login automatically without asking login ID
10 | UC-3 | Mobile | Uncheck the autologin checkbox and exit the app Run the application and check login screen | User login screen should be shown
11 | UC-3 | Mobile | Reinstall the mobile application and try to login with the same account | User can login with the same account
12 | UC-4 | Mobile | After login, check the screen | At initial state , No Receipt screen will be shown After adding receipt, list of receipt will be shown
13 | UC-4 | Mobile | Check the item of list | Receipt information will have date, store, category, total, tag, receipt image, status of sync
14 | UC-4 | Mobile | Select the item of list | If the item of list is selected, detail view of receipt will be shown
15 | UC-4 | Mobile | Long Click on the item of list | Dialog popup will be shown to get confirm to delete the item
16 | UC-5 | Mobile | Check detailed view of receipt | The detailed view will have image of the receipt, store name, date of purchase, category, tag, comment, total, payment method. Edit button will be shown at the bottom
19 | UC-5 | Both | Select one of items for viewing details | At detail, it will show receipt's detail information such as date of purchase, store, category, total, comment, tag, picture of receipt.
20 | UC-6 | Mobile | At mobile, go to the menu of create receipt | The phone will be in preview state of taking picture
21 | UC-6 | Mobile | Check preview screen | There shoule be some feedback to the user to help taking picture of receipt for better character recognition
22 | UC-6 | Mobile | There's menu to take picture | If user select taking picture, result of character recognition for total and store name will be presented to the user And User can edit the information
23 | UC-6 | Mobile | Save the result | After saving the information, there's feedback it was saved succssfully or not and will be redirected to the list of receipt
24 | UC-6 | Mobile | Scan a receipt for a store listed in the autocomplete | After taking photo, the correct store name is found by OCR.
25 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete | After taking photo, the correct payment method is found by OCR.
26 | UC-6 | Mobile | Scan a receipt with a store name not found in the autocomplete | First line of text is suggested as store name
27 | UC-6 | Mobile | Scan a receipt with a store name not found in autocomplete and allow user to add new store name | After taking photo, on Add Receipt screen a store name can be edited and added
28 | UC-6 | Mobile | Scan a receipt and make sure total is found by O.C.R. | The total is found and completed by the O.C.R.
29 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete but change it before saving | The user can change a payment method before saving
30 | UC-6 | Mobile | Make sure the image of a receipt is saved after scanning | Bounding boxes are removed from the image
31 | UC-6 | Mobile | During scanning of image before taking photo, display results found so far for user to see | The displayed indicators should be in synchronization with the ocr result
32 | UC-6 | Mobile | Scan a store name printed with stylized text, logo, etc. | O.C.R. should be able to recognize some special fonts, not always but at least some cases should work.
33 | UC-6 | Mobile | Scan a receipt with a date that includes the month fully written out, i.e. "January", "July", etc. | All parts of the date should be found by the O.C.R.
34 | UC-6 | Mobile | Scan a receipt with a date of format dd-mm-yyyy | The O.C.R. should recognize the '-' delimiter and process the date
35 | UC-6 | Mobile | Scan a receipt with a date of format dd/mm/yyyy | The O.C.R. should recognize the '/' delimiter and process the date
36 | UC-6 | Mobile | Scan a receipt with a date that includes three letters of the month written out, i.e. "Jan", "Jul", etc. | The O.C.R. should find the date and scan it correctly
37 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm-dd-yyyy | The O.C.R. should recognize the '-' delimiter and process the date
38 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm/dd/yyyy | The O.C.R. should recognize the '/' delimiter and process the date
39 | UC-7 | Mobile | Select edit button at detail view | Edit screen of the receipt will be shown
40 | UC-7 | Mobile | Modify value at edit view and save | Modified value should be applied and it will goto list view
41 | UC-6 | Mobile | Cacel the result | If user select cancel instead of save, it will go to the preview status
42 | UC-7 | Mobile | At mobile, go to edit recipt information which is presented at list view of receipt or detail view of receipt | User can edit receipt information manually and after saving it will go to previous state.
43 | UC-7 | Both | After Sync, check the updated information at web app | After sync, updated receipt information can be seen at Web app
44 | UC-8 | Mobile | Delete one of items and check the list of recipt | User can delete one or more receipt at the receipt list or receipt detail
45 | UC-9 | Both | Search one recipt with keyword at the search menu box | User can search receipt by keywords
46 | UC-9 | Both | Select a filter at the list | User can filter receipt by store, category, date
47 | UC-10 | Both | Select Adding Tag at the receipt list | User can add tag at the list of receipt or detail view of receipt
48 | UC-10 | Both | Select Addinng Category for the store | There is a menu for adding or modifying store's category
49 | UC-2 | Web | Login, check input validation of email and password | Invalid input values are not allowed and shows message to User
50 | UC-2 | Web | Login, 'Log In' button is disable | User input valid value at email and password input box then 'Log In' button turns enable to perform login
51 | UC-2 | Web | Loggedin successfully | redirect to user dashboard page
52 | UC-2 | Web | Clicking Logout | User access token is delete and redirect to home page (about page)
53 | UC-1 | Web | SignUp page | When user clicks SignUp link, move to SignUp page. User resgister with only email and password
54 | UC-1 | Web | SignUp, Clicking 'SignUp' button | Email, password input values are validate. Invalid value exist, pop-up message will be showing to notify
55 | UC-5 | Web | Unauthorized user trys to access loggedin pages | redirect to the 'Login' pages
56 | UC-12 | Web | Dashboard, displaying each data | data retrieve from database correctly, if no data in database show no data in it
57 | UC-12 | Web | Dashboard, chart can export to several types of tiles | Export chart to Print, PDF, JPEG, PNG, SVG files
58 | UC-12 | Web | Dashboard, edit user's basic profile and change password | User can modify username, firstname, lastname, user potho, and changing password
59 | UC-12 | Web | Dashboard, upload user's photo in user profile pop-up window | Only allows image type of file and validate less than 2MB file size, if invalid shows message to user
60 | UC-12 | Web | Dashboard, clicking each of tag name in Tags cloud section | Pop-up window to show receipts list related with selected tag
61 | UC-12 | Web | Dashboard, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt
62 | UC-4 | Web | Receipts, show user's receipt data | retrieve from receipts data from database with pagination
63 | UC-4 | Web | Receipts, pagination function | Previous and Next button work correctly, page unit works correctly
64 | UC-4 | Web | Receipts, Search function | When user input value in search text, it filters and show the result in the table correctly
65 | UC-4 | Web | Receipts, Sorted by clicking each table title | Except comment, sorted by store name, data, total, number of items out of receipts list
66 | UC-4 | Web | Receipts, Export Excel file function | When user clicks 'Export Excel' icon, downloading the excel file including contents of table
67 | UC-5 | Web | View Receipt, Show data and image of receipt | Display data from database, and show image of photo if attached
68 | UC-5 | Web | View Receipt, clicking 'Edit button' | Move to Edit Page with related data of the receipt
69 | UC-5 | Web | View Receipt, clicking 'Tag's button related with the receipt | Pop-up window to show receipts list related with selected tag
70 | UC-5 | Web | View Receipt, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt
71 | UC-6 | Web | Add Receipt, Data editable | Store, Category, Price, Number of items are required and validation check. Comment is optional, but only allowed 140 letters length. Other required input value will be validated, when invalid value exist, pop-up message to notice.
72 | UC-6 | Web | Add Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data
73 | UC-7 | Web | Edit Receipt, Data editable | Store, Category, Price, Number of items, comment, image of receipt are editable
74 | UC-7 | Web | Edit Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data
75 | UC-8 | Web | Edit Receipt, Clicking 'Delete Receipt' button | pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete receipt and remove relation with related with data and then redirect to 'Receipts' page. When clicking 'Cancel', close pop up window and back to Edit Receipt page
76 | UC-7 | Web | Edit Receipt, validation of input values | Editable values are validated where each of values is valid or not
77 | UC-7 | Web | Edit Receipt, uploading image file of receipt | Allow image type files are allowed to be uploaded and validate less than 2MB file size
78 | UC-11 | Web | Chart, Clicking 'chart' menu link in the navigation bar | Move to 'Charts' page and display various type of chars and graphs. Monthly consumption, Comparison bar chart, Tag tendency, Store Amount, Category, Store, Tag, and Tag Progress Bar chart which are all retrived from database
79 | UC-11 | Web | Chart, Changing the period of month in 'Montly consumption' title bar | Changing all charts and graphs according to selected period of months and display data that retrieve from database
80 | UC-11 | Web | Chart, Moving mouse on the each value of chart or graph | Pop up the tooltip and show the value of each chart or graph
81 | UC-11 | Web | Chart, Clicking pdf icon button on the right top of the title bar | Download pdf file as selected chart in Monthly comsumption, Comparison, Tag Tendancy, and Store Amount Charts
82 | UC-10 | Web | Categories, clicking 'Config-Categories' menu in the navigation bar | Shows user's customizing category data which retrieved from database with pagination
83 | UC-10 | Web | Categories, pagination function | Previous and Next button work correctly, page unit works correctly
84 | UC-10 | Web | Categories, Search function | When user input value in search text, it filters and show the result in the table correctly
85 | UC-10 | Web | Categories, Sorted by clicking category name | sorted by category name as descending or ascending
86 | UC-10 | Web | Categories, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected category
87 | UC-10 | Web | Categories, Clicking 'Add Category' button | Move to Add Page
88 | UC-10 | Web | Add Category, input category name | User is allow to input category name, but validate invalid input value such empty value, already existing name
89 | UC-10 | Web | Add Category, Clicking 'Save Category' button | if category name is valid, 'Save Category' button is enabled, after clicking 'Save Category' button, store new category name into database, and then redirect to 'Categories' page
90 | UC-10 | Web | Edit Category, 'Delete Category' button is disabled | When category is used by store(s), user is not allowed to delete category, so 'Delete Category' button is disabled
91 | UC-10 | Web | Edit Category, Edit Category Name | Category Name is editable, but validate invalid input value such empty value, already existing name
92 | UC-10 | Web | Edit Category, Clicking 'Save Category' button | Save category name and redirect to 'Categories' page
93 | UC-10 | Web | Edit Category, Clicking 'Delete Category' | When clicking enabled 'Delete Category', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete catgory and then redirect to 'Categories' page. When clicking 'Cancel', close the pop up window and back to Edit Category page
94 | UC-10 | Web | Tags, clicking 'Config-Tags' menu in the navigation bar | Shows user's customizing tag data which retrieved from database with pagination
95 | UC-10 | Web | Tags, pagination function | Previous and Next button work correctly, page unit works correctly
96 | UC-10 | Web | Tags, Search function | When user input value in search text, it filters and show the result in the table correctly
97 | UC-10 | Web | Tags, Sorted by clicking category name | sorted by tag name as descending or ascending
98 | UC-10 | Web | Tags, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected tag
99 | UC-10 | Web | Tags, Clicking 'Add Tag' button | Move to Add Page
100 | UC-10 | Web | Add Tag, input tag name | User is allow to input tag name, but validate invalid input value such empty value, already existing name
101 | UC-10 | Web | Add Tag, Clicking 'Save Tag' button | if tag name is valid, 'Save Tag' button is enabled, after clicking 'Save Tag' button, store new tag name into database, and then redirect to 'Tags' page
102 | UC-10 | Web | Edit Tag, 'DeleteTag' button is disabled | When tag is used by receipt(s), user is not allowed to delete tag, so 'Delete Tag' button is disabled
103 | UC-10 | Web | Edit Tag, Edit Tag Name | Tag Name is editable, but validate invalid input value such empty value, already existing name
104 | UC-10 | Web | Edit Tag, Clicking 'Save Tag' button | Save tag name and redirect to 'Tags' page
105 | UC-10 | Web | Edit Tag, Clicking 'Delete Tag' | When clicking enabled 'Delete Tag', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete tag and then redirect to 'Tags' page. When clicking 'Cancel', close the pop up window and back to Edit Tag page
106 | UC-10 | Web | Stores, clicking 'Config-Stores' menu in the navigation bar | Shows user's customizing store data which retrieved from database with pagination
107 | UC-10 | Web | Stores, pagination function | Previous and Next button work correctly, page unit works correctly
108 | UC-10 | Web | Stores, Search function | When user input value in search text, it filters and show the result in the table correctly
109 | UC-10 | Web | Stores, Sorted by clicking store name | sorted by store name as descending or ascending
110 | UC-10 | Web | Stores, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected store
111 | UC-10 | Web | Stores, Clicking 'Add Store' button | Move to Add Page
112 | UC-10 | Web | Add Store, input store name | User is allow to input store name and select category, but validate invalid input value such empty value, already existing name, and if category is selected or not
113 | UC-10 | Web | Add Store, Clicking 'Save Store' button | if store name is valid, 'Save Store' button is enabled, after clicking 'Save Store' button, save new store name with relation to category into database, and then redirect to 'Stores' page
114 | UC-10 | Web | Edit Store, 'Delete Store' button is disabled | When store is used by receipt(s), user is not allowed to delete store, so 'Delete Store' button is disabled
115 | UC-10 | Web | Edit Store, Edit Store Name and select category name | Store name is editable and allow to re-select category accordingly, but validate invalid input value such empty value, already existing name, and if category is selected or not
116 | UC-10 | Web | Edit Store, Clicking 'Save Store' button | Save store name and redirect to 'Stores' page
117 | UC-10 | Web | Edit Store, Clicking 'Delete Store' | When clicking enabled 'Delete Store', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete store with disconnecting relation to category and then redirect to 'Stores' page. When clicking 'Cancel', close the pop up window and back to Edit Store page
118 | UC-13 | Web | Groups, Clicking 'Groups' on the navigation bar | Move to 'Groups' page
119 | UC-13 | Web | Groups, showing group information | If user has user's already created group, then display group name as owner. If user has joined group(s) as a member, then display joined group(s) name
120 | UC-13 | Web | Groups, Clicking 'Add Group' button | When user haven't created a group, 'Add Group' button is visible. After clicking 'Add Group' button, move to 'Add Group' page
121 | UC-13 | Web | Add Group, input group name, group description | Group name is required and description is optional. Validating group name such as empty value and less than 30 letters. Also description is limited less than 140 letters
122 | UC-13 | Web | Add Group, Clicking 'Save Group' button | Save group name and descript and redirect to 'Groups' page
123 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as owner' | Move to eighter of 'Group Receipts', 'View Group', or 'Edit Group' pages
124 | UC-13 | Web | View Group, show group detailed information | display data from database, and show member(s) email list if the group has member(s). If the loggedin user is an owner of group, shows additional buttons such as 'Edit Group', 'Group Categories', 'Group Stores', and 'Group Tags'
125 | UC-13 | Web | View Group, clicking each of buttons | move to related pages such as 'Group Receipts', 'Group Charts'
126 | UC-13 | Web | Edit Group, edit group name, description | Group name and description is editable
127 | UC-13 | Web | Edit Group, 'Delete Group' is disabled | If group already has member(s), owner is not allowed to delete group, so the 'Delete Group' button is disabled
128 | UC-13 | Web | Edit Group, Clicking 'Invitation' button | Group owner is allowed to invite user as group member with email, after clicking 'Invitation' button, email is added in the 'Invitation list'
129 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Invitation list' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Invitation list'. When clicking 'Cancel', close the pop up window and back to Edit Group page
130 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Leaving Group' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Leaving Group'. The member will not show any more When clicking 'Cancel', close the pop up window and back to Edit Group page
131 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as member' | Move to relevent page in case of 'Receipt' and 'View Details'
132 | UC-13 | Web | Groups, Clicking 'Leave Group' font icon button in 'Group as member' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, send request notification to group owner. When clicking 'Cancel', close the pop up window and back to Group page
133 | UC-13 | Web | Groups, Showing notification | Member can receive notification from group owner's invitation as member
134 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user
135 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving
136 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving

## Iteration1
Schedule
Planned Start Date |  | Planned End Date |  | Actual Start Date |  | Actual End Date
2016-06-24 |  | 2016-06-26
SUM
Total TC | Tested TC (Except N/A) | Total Pass | Total Fail | Total Resolved | Pass Rate | Resolved Rate
58 | 58 | 17 | 7 | 0 | 29.31% | 0%
ID | UseCaseID | Device | Test Case Description | Expected Result | Actual Result Description | Pass/Fail | Resolved
1 | UC-1 | Both | At login screen, check the availability of sign up menu and check the functionality of sign up menu | There is sign up button or link is available and if user select the button, user can enter their information to sign up |  | Pass
2 | UC-1 | Both | If some required field is unfilled, check the submit button | If user miss some required field at the sign up form, submit button should be inactive At mobile, after user select submit, it will be notified required field is not filled |  | Pass
3 | UC-1 | Both | Filling out sign up form and submit the form | There is a message feedback after user successfully submit the register form. After signing up, user can log in the system automatically |  | Pass
4 | UC-1 | Both | After signup at mobile, try to sign in at web app with the same account | User can login at web app |  | Pass
5 | UC-1 | Both | After signup at web app, try to sign in at mobile app with same account | User can login at mobile app |  | Pass
6 | UC-2 | Both | Check functionality of login | User can login with registered email id |  | Pass
7 | UC-2 | Mobile | Check the existence of auto login checkbox | At login form screen, auto login check box should exist |  | Pass
8 | UC-3 | Mobile | If user check auto login checkbox, try to login and Check setting menu | After login successfully, autologin checkbox should be checked |  | Pass
9 | UC-3 | Mobile | Exit with autologin checkbox checked, and try to rerun the app | User can login automatically without asking login ID |  | Pass
10 | UC-3 | Mobile | Uncheck the autologin checkbox and exit the app Run the application and check login screen | User login screen should be shown |  | Pass
11 | UC-3 | Mobile | Reinstall the mobile application and try to login with the same account | User can login with the same account |  | Pass
12 | UC-4 | Mobile | After login, check the screen | At initial state , No Receipt screen will be shown After adding receipt, list of receipt will be shown |  | Pass
13 | UC-4 | Mobile | Check the item of list | Receipt information will have date, store, category, total, tag, receipt image, status of sync |  | Pass
14 | UC-4 | Mobile | Select the item of list | If the item of list is selected, detail view of receipt will be shown |  | Pass
15 | UC-4 | Mobile | Long Click on the item of list | Dialog popup will be shown to get confirm to delete the item |  | Pass
16 | UC-5 | Mobile | Check detailed view of receipt | The detailed view will have image of the receipt, store name, date of purchase, category, tag, comment, total, payment method. Edit button will be shown at the bottom |  | Pass
19 | UC-5 | Both | Select one of items for viewing details | At detail, it will show receipt's detail information such as date of purchase, store, category, total, comment, tag, picture of receipt. |  | Pass
20 | UC-6 | Mobile | At mobile, go to the menu of create receipt | The phone will be in preview state of taking picture |  | Pass
21 | UC-6 | Mobile | Check preview screen | There shoule be some feedback to the user to help taking picture of receipt for better character recognition |  | Pass
22 | UC-6 | Mobile | There's menu to take picture | If user select taking picture, result of character recognition for total and store name will be presented to the user And User can edit the information |  | Pass
23 | UC-6 | Mobile | Save the result | After saving the information, there's feedback it was saved succssfully or not and will be redirected to the list of receipt |  | Pass
24 | UC-6 | Mobile | Scan a receipt for a store listed in the autocomplete | After taking photo, the correct store name is found by OCR. |  | Pass
25 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete | After taking photo, the correct payment method is found by OCR. |  | Fail
26 | UC-6 | Mobile | Scan a receipt with a store name not found in the autocomplete | First line of text is suggested as store name |  | Fail
27 | UC-6 | Mobile | Scan a receipt with a store name not found in autocomplete and allow user to add new store name | After taking photo, on Add Receipt screen a store name can be edited and added |  | Fail
28 | UC-6 | Mobile | Scan a receipt and make sure total is found by O.C.R. | The total is found and completed by the O.C.R. |  | Fail
29 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete but change it before saving | The user can change a payment method before saving |  | Fail
30 | UC-6 | Mobile | Make sure the image of a receipt is saved after scanning | Bounding boxes are removed from the image |  | Fail
31 | UC-6 | Mobile | During scanning of image before taking photo, display results found so far for user to see | The displayed indicators should be in synchronization with the ocr result |  | Fail
32 | UC-6 | Mobile | Scan a store name printed with stylized text, logo, etc. | O.C.R. should be able to recognize some special fonts, not always but at least some cases should work. |  | Fail
33 | UC-6 | Mobile | Scan a receipt with a date that includes the month fully written out, i.e. "January", "July", etc. | All parts of the date should be found by the O.C.R. |  | Fail
34 | UC-6 | Mobile | Scan a receipt with a date of format dd-mm-yyyy | The O.C.R. should recognize the '-' delimiter and process the date |  | Fail
35 | UC-6 | Mobile | Scan a receipt with a date of format dd/mm/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Scanning for too few characters produces incorrect results | Fail | No
36 | UC-6 | Mobile | Scan a receipt with a date that includes three letters of the month written out, i.e. "Jan", "Jul", etc. | The O.C.R. should find the date and scan it correctly | Tested with Visa successfully | Pass | Yes
37 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm-dd-yyyy | The O.C.R. should recognize the '-' delimiter and process the date | Works as expected | Pass | Yes
38 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm/dd/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Works as expected | Pass | Yes
39 | UC-7 | Mobile | Select edit button at detail view | Edit screen of the receipt will be shown | Subtotal is sometimes found by mistake. | Fail | No
40 | UC-7 | Mobile | Modify value at edit view and save | Modified value should be applied and it will goto list view | Works as expected | Pass | Yes
41 | UC-6 | Mobile | Cacel the result | If user select cancel instead of save, it will go to the preview status | Image saved but bounding boxes still present | Fail | No
42 | UC-7 | Mobile | At mobile, go to edit recipt information which is presented at list view of receipt or detail view of receipt | User can edit receipt information manually and after saving it will go to previous state. | Data displayed does always update when result changes | Fail | No
43 | UC-7 | Both | After Sync, check the updated information at web app | After sync, updated receipt information can be seen at Web app | Works as exppected | Pass | Yes
44 | UC-8 | Mobile | Delete one of items and check the list of recipt | User can delete one or more receipt at the receipt list or receipt detail | Works as expected | Pass | Yes
45 | UC-9 | Both | Search one recipt with keyword at the search menu box | User can search receipt by keywords | Works as expected | Pass | Yes
46 | UC-9 | Both | Select a filter at the list | User can filter receipt by store, category, date | Works as expected | Pass | Yes
47 | UC-10 | Both | Select Adding Tag at the receipt list | User can add tag at the list of receipt or detail view of receipt | Works as expected | Pass | Yes
48 | UC-10 | Both | Select Addinng Category for the store | There is a menu for adding or modifying store's category | Date not found | Fail | No
49 | UC-2 | Web | Login, check input validation of email and password | Invalid input values are not allowed and shows message to User | Works as expected | Pass
50 | UC-2 | Web | Login, 'Log In' button is disable | User input valid value at email and password input box then 'Log In' button turns enable to perform login | Works as expected | Pass
51 | UC-2 | Web | Loggedin successfully | redirect to user dashboard page | Works as expected | Pass
52 | UC-2 | Web | Clicking Logout | User access token is delete and redirect to home page (about page) | Works as expected | Pass
53 | UC-1 | Web | SignUp page | When user clicks SignUp link, move to SignUp page. User resgister with only email and password | Works as expected | Pass
54 | UC-1 | Web | SignUp, Clicking 'SignUp' button | Email, password input values are validate. Invalid value exist, pop-up message will be showing to notify | Works as expected | Pass
55 | UC-5 | Web | Unauthorized user trys to access loggedin pages | redirect to the 'Login' pages | Works as expected | Pass
56 | UC-10 | Web | Categories, clicking 'Config-Categories' menu in the navigation bar | Shows user's customizing category data which retrieved from database with pagination | Works as expected | Pass
57 | UC-10 | Web | Categories, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
58 | UC-10 | Web | Categories, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
59 | UC-10 | Web | Categories, Sorted by clicking category name | sorted by category name as descending or ascending | Works as expected | Pass
60 | UC-10 | Web | Categories, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected category | Works as expected | Pass
61 | UC-10 | Web | Categories, Clicking 'Add Category' button | Move to Add Page | Works as expected | Pass
62 | UC-10 | Web | Add Category, input category name | User is allow to input category name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
63 | UC-10 | Web | Add Category, Clicking 'Save Category' button | if category name is valid, 'Save Category' button is enabled, after clicking 'Save Category' button, store new category name into database, and then redirect to 'Categories' page | Works as expected | Pass
64 | UC-10 | Web | Edit Category, 'Delete Category' button is disabled | When category is used by store(s), user is not allowed to delete category, so 'Delete Category' button is disabled | Works as expected | Pass
65 | UC-10 | Web | Edit Category, Edit Category Name | Category Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
66 | UC-10 | Web | Edit Category, Clicking 'Save Category' button | Save category name and redirect to 'Categories' page | Works as expected | Pass
67 | UC-10 | Web | Edit Category, Clicking 'Delete Category' | When clicking enabled 'Delete Category', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete catgory and then redirect to 'Categories' page. When clicking 'Cancel', close the pop up window and back to Edit Category page | Works as expected | Pass
68 | UC-10 | Web | Tags, clicking 'Config-Tags' menu in the navigation bar | Shows user's customizing tag data which retrieved from database with pagination | Works as expected | Pass
69 | UC-10 | Web | Tags, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
70 | UC-10 | Web | Tags, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
71 | UC-10 | Web | Tags, Sorted by clicking category name | sorted by tag name as descending or ascending | Works as expected | Pass
72 | UC-10 | Web | Tags, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected tag | Works as expected | Pass
73 | UC-10 | Web | Tags, Clicking 'Add Tag' button | Move to Add Page | Works as expected | Pass
74 | UC-10 | Web | Add Tag, input tag name | User is allow to input tag name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
75 | UC-10 | Web | Add Tag, Clicking 'Save Tag' button | if tag name is valid, 'Save Tag' button is enabled, after clicking 'Save Tag' button, store new tag name into database, and then redirect to 'Tags' page | Works as expected | Pass
76 | UC-10 | Web | Edit Tag, 'DeleteTag' button is disabled | When tag is used by receipt(s), user is not allowed to delete tag, so 'Delete Tag' button is disabled | Works as expected | Pass
77 | UC-10 | Web | Edit Tag, Edit Tag Name | Tag Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
78 | UC-10 | Web | Edit Tag, Clicking 'Save Tag' button | Save tag name and redirect to 'Tags' page | Works as expected | Pass
79 | UC-10 | Web | Edit Tag, Clicking 'Delete Tag' | When clicking enabled 'Delete Tag', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete tag and then redirect to 'Tags' page. When clicking 'Cancel', close the pop up window and back to Edit Tag page | Works as expected | Pass

## Iteration2
Schedule
Planned Start Date |  | Planned End Date |  | Actual Start Date |  | Actual End Date
2016-07-01 |  | 2016-07-04
SUM
Total TC | Tested TC (Except N/A) | Total Pass | Total Fail | Total Resolved | Pass Rate | Resolved Rate
58 | 58 | 21 | 3 | 0 | 36.21% | 0%
ID | UseCaseID | Device | Test Case Description | Expected Result | Actual Result Description | Pass/Fail | Resolved
1 | UC-1 | Both | At login screen, check the availability of sign up menu and check the functionality of sign up menu | There is sign up button or link is available and if user select the button, user can enter their information to sign up |  | Pass
2 | UC-1 | Both | If some required field is unfilled, check the submit button | If user miss some required field at the sign up form, submit button should be inactive At mobile, after user select submit, it will be notified required field is not filled |  | Pass
3 | UC-1 | Both | Filling out sign up form and submit the form | There is a message feedback after user successfully submit the register form. After signing up, user can log in the system automatically |  | Pass
4 | UC-1 | Both | After signup at mobile, try to sign in at web app with the same account | User can login at web app |  | Pass
5 | UC-1 | Both | After signup at web app, try to sign in at mobile app with same account | User can login at mobile app |  | Pass
6 | UC-2 | Both | Check functionality of login | User can login with registered email id |  | Pass
7 | UC-2 | Mobile | Check the existence of auto login checkbox | At login form screen, auto login check box should exist |  | Pass
8 | UC-3 | Mobile | If user check auto login checkbox, try to login and Check setting menu | After login successfully, autologin checkbox should be checked |  | Pass
9 | UC-3 | Mobile | Exit with autologin checkbox checked, and try to rerun the app | User can login automatically without asking login ID |  | Pass
10 | UC-3 | Mobile | Uncheck the autologin checkbox and exit the app Run the application and check login screen | User login screen should be shown |  | Pass
11 | UC-3 | Mobile | Reinstall the mobile application and try to login with the same account | User can login with the same account |  | Pass
12 | UC-4 | Mobile | After login, check the screen | At initial state , No Receipt screen will be shown After adding receipt, list of receipt will be shown |  | Pass
13 | UC-4 | Mobile | Check the item of list | Receipt information will have date, store, category, total, tag, receipt image, status of sync |  | Pass
14 | UC-4 | Mobile | Select the item of list | If the item of list is selected, detail view of receipt will be shown |  | Pass
15 | UC-4 | Mobile | Long Click on the item of list | Dialog popup will be shown to get confirm to delete the item |  | Pass
16 | UC-5 | Mobile | Check detailed view of receipt | The detailed view will have image of the receipt, store name, date of purchase, category, tag, comment, total, payment method. Edit button will be shown at the bottom |  | Pass
19 | UC-5 | Both | Select one of items for viewing details | At detail, it will show receipt's detail information such as date of purchase, store, category, total, comment, tag, picture of receipt. |  | Pass
20 | UC-6 | Mobile | At mobile, go to the menu of create receipt | The phone will be in preview state of taking picture |  | Pass
21 | UC-6 | Mobile | Check preview screen | There shoule be some feedback to the user to help taking picture of receipt for better character recognition |  | Pass
22 | UC-6 | Mobile | There's menu to take picture | If user select taking picture, result of character recognition for total and store name will be presented to the user And User can edit the information |  | Pass
23 | UC-6 | Mobile | Save the result | After saving the information, there's feedback it was saved succssfully or not and will be redirected to the list of receipt |  | Pass
24 | UC-6 | Mobile | Scan a receipt for a store listed in the autocomplete | After taking photo, the correct store name is found by OCR. |  | Pass
25 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete | After taking photo, the correct payment method is found by OCR. |  | Pass
26 | UC-6 | Mobile | Scan a receipt with a store name not found in the autocomplete | First line of text is suggested as store name |  | Pass
27 | UC-6 | Mobile | Scan a receipt with a store name not found in autocomplete and allow user to add new store name | After taking photo, on Add Receipt screen a store name can be edited and added |  | Pass
28 | UC-6 | Mobile | Scan a receipt and make sure total is found by O.C.R. | The total is found and completed by the O.C.R. |  | Fail
29 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete but change it before saving | The user can change a payment method before saving |  | Pass
30 | UC-6 | Mobile | Make sure the image of a receipt is saved after scanning | Bounding boxes are removed from the image |  | Fail
31 | UC-6 | Mobile | During scanning of image before taking photo, display results found so far for user to see | The displayed indicators should be in synchronization with the ocr result |  | Fail
32 | UC-6 | Mobile | Scan a store name printed with stylized text, logo, etc. | O.C.R. should be able to recognize some special fonts, not always but at least some cases should work. |  | Pass
33 | UC-6 | Mobile | Scan a receipt with a date that includes the month fully written out, i.e. "January", "July", etc. | All parts of the date should be found by the O.C.R. |  | Pass
34 | UC-6 | Mobile | Scan a receipt with a date of format dd-mm-yyyy | The O.C.R. should recognize the '-' delimiter and process the date |  | Pass
35 | UC-6 | Mobile | Scan a receipt with a date of format dd/mm/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Scanning for too few characters produces incorrect results | Fail | No
36 | UC-6 | Mobile | Scan a receipt with a date that includes three letters of the month written out, i.e. "Jan", "Jul", etc. | The O.C.R. should find the date and scan it correctly | Tested with Visa successfully | Pass | Yes
37 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm-dd-yyyy | The O.C.R. should recognize the '-' delimiter and process the date | Works as expected | Pass | Yes
38 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm/dd/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Works as expected | Pass | Yes
39 | UC-7 | Mobile | Select edit button at detail view | Edit screen of the receipt will be shown | Subtotal is sometimes found by mistake. | Fail | No
40 | UC-7 | Mobile | Modify value at edit view and save | Modified value should be applied and it will goto list view | Works as expected | Pass | Yes
41 | UC-6 | Mobile | Cacel the result | If user select cancel instead of save, it will go to the preview status | Image saved but bounding boxes still present | Fail | No
42 | UC-7 | Mobile | At mobile, go to edit recipt information which is presented at list view of receipt or detail view of receipt | User can edit receipt information manually and after saving it will go to previous state. | Data displayed does always update when result changes | Fail | No
43 | UC-7 | Both | After Sync, check the updated information at web app | After sync, updated receipt information can be seen at Web app | Works as exppected | Pass | Yes
44 | UC-8 | Mobile | Delete one of items and check the list of recipt | User can delete one or more receipt at the receipt list or receipt detail | Works as expected | Pass | Yes
45 | UC-9 | Both | Search one recipt with keyword at the search menu box | User can search receipt by keywords | Works as expected | Pass | Yes
46 | UC-9 | Both | Select a filter at the list | User can filter receipt by store, category, date | Works as expected | Pass | Yes
47 | UC-10 | Both | Select Adding Tag at the receipt list | User can add tag at the list of receipt or detail view of receipt | Works as expected | Pass | Yes
48 | UC-10 | Both | Select Addinng Category for the store | There is a menu for adding or modifying store's category | Date not found | Fail | No
49 | UC-10 | Web | Stores, clicking 'Config-Stores' menu in the navigation bar | Shows user's customizing store data which retrieved from database with pagination | Works as expected | Pass
50 | UC-10 | Web | Stores, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
51 | UC-10 | Web | Stores, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
52 | UC-10 | Web | Stores, Sorted by clicking store name | sorted by store name as descending or ascending | Works as expected | Pass
53 | UC-10 | Web | Stores, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected store | Works as expected | Pass
54 | UC-10 | Web | Stores, Clicking 'Add Store' button | Move to Add Page | Works as expected | Pass
55 | UC-10 | Web | Add Store, input store name | User is allow to input store name and select category, but validate invalid input value such empty value, already existing name, and if category is selected or not | Works as expected | Pass
56 | UC-10 | Web | Add Store, Clicking 'Save Store' button | if store name is valid, 'Save Store' button is enabled, after clicking 'Save Store' button, save new store name with relation to category into database, and then redirect to 'Stores' page | Works as expected | Pass
57 | UC-10 | Web | Edit Store, 'Delete Store' button is disabled | When store is used by receipt(s), user is not allowed to delete store, so 'Delete Store' button is disabled | Works as expected | Pass
58 | UC-10 | Web | Edit Store, Edit Store Name and select category name | Store name is editable and allow to re-select category accordingly, but validate invalid input value such empty value, already existing name, and if category is selected or not | Works as expected | Pass
59 | UC-10 | Web | Edit Store, Clicking 'Save Store' button | Save store name and redirect to 'Stores' page | Works as expected | Pass
60 | UC-10 | Web | Edit Store, Clicking 'Delete Store' | When clicking enabled 'Delete Store', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete store with disconnecting relation to category and then redirect to 'Stores' page. When clicking 'Cancel', close the pop up window and back to Edit Store page | Works as expected | Pass
61 | UC-4 | Web | Receipts, show user's receipt data | retrieve from receipts data from database with pagination | Works as expected | Pass
62 | UC-4 | Web | Receipts, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
63 | UC-4 | Web | Receipts, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
64 | UC-4 | Web | Receipts, Sorted by clicking each table title | Except comment, sorted by store name, data, total, number of items out of receipts list | Works as expected | Pass
65 | UC-4 | Web | Receipts, Export Excel file function | When user clicks 'Export Excel' icon, downloading the excel file including contents of table | Works as expected | Pass
66 | UC-5 | Web | View Receipt, Show data and image of receipt | Display data from database, and show image of photo if attached | Works as expected | Pass
67 | UC-5 | Web | View Receipt, clicking 'Edit button' | Move to Edit Page with related data of the receipt | Works as expected | Pass
68 | UC-5 | Web | View Receipt, clicking 'Tag's button related with the receipt | Pop-up window to show receipts list related with selected tag | Works as expected | Pass
69 | UC-5 | Web | View Receipt, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt | Works as expected | Pass
70 | UC-6 | Web | Add Receipt, Data editable | Store, Category, Price, Number of items are required and validation check. Comment is optional, but only allowed 140 letters length. Other required input value will be validated, when invalid value exist, pop-up message to notice. | Works as expected | Pass
71 | UC-6 | Web | Add Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Works as expected | Pass
72 | UC-7 | Web | Edit Receipt, Data editable | Store, Category, Price, Number of items, comment, image of receipt are editable | Works as expected | Pass
73 | UC-7 | Web | Edit Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Works as expected | Pass
74 | UC-8 | Web | Edit Receipt, Clicking 'Delete Receipt' button | pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete receipt and remove relation with related with data and then redirect to 'Receipts' page. When clicking 'Cancel', close pop up window and back to Edit Receipt page | Works as expected | Pass
75 | UC-7 | Web | Edit Receipt, validation of input values | Editable values are validated where each of values is valid or not | Works as expected | Pass
76 | UC-7 | Web | Edit Receipt, uploading image file of receipt | Allow image type files are allowed to be uploaded and validate less than 2MB file size | Works as expected | Pass

## Iteration3
Schedule
Planned Start Date |  | Planned End Date |  | Actual Start Date |  | Actual End Date
2016-07-22 |  | 2016-07-25
SUM
Total TC | Tested TC (Except N/A) | Total Pass | Total Fail | Total Resolved | Pass Rate | Resolved Rate
58 | 58 | 23 | 1 | 0 | 39.66% | 0%
ID | UseCaseID | Device | Test Case Description | Expected Result | Actual Result Description | Pass/Fail | Resolved
1 | UC-1 | Both | At login screen, check the availability of sign up menu and check the functionality of sign up menu | There is sign up button or link is available and if user select the button, user can enter their information to sign up |  | Pass
2 | UC-1 | Both | If some required field is unfilled, check the submit button | If user miss some required field at the sign up form, submit button should be inactive At mobile, after user select submit, it will be notified required field is not filled |  | Pass
3 | UC-1 | Both | Filling out sign up form and submit the form | There is a message feedback after user successfully submit the register form. After signing up, user can log in the system automatically |  | Pass
4 | UC-1 | Both | After signup at mobile, try to sign in at web app with the same account | User can login at web app |  | Pass
5 | UC-1 | Both | After signup at web app, try to sign in at mobile app with same account | User can login at mobile app |  | Pass
6 | UC-2 | Both | Check functionality of login | User can login with registered email id |  | Pass
7 | UC-2 | Mobile | Check the existence of auto login checkbox | At login form screen, auto login check box should exist |  | Pass
8 | UC-3 | Mobile | If user check auto login checkbox, try to login and Check setting menu | After login successfully, autologin checkbox should be checked |  | Pass
9 | UC-3 | Mobile | Exit with autologin checkbox checked, and try to rerun the app | User can login automatically without asking login ID |  | Pass
10 | UC-3 | Mobile | Uncheck the autologin checkbox and exit the app Run the application and check login screen | User login screen should be shown |  | Pass
11 | UC-3 | Mobile | Reinstall the mobile application and try to login with the same account | User can login with the same account |  | Pass
12 | UC-4 | Mobile | After login, check the screen | At initial state , No Receipt screen will be shown After adding receipt, list of receipt will be shown |  | Pass
13 | UC-4 | Mobile | Check the item of list | Receipt information will have date, store, category, total, tag, receipt image, status of sync |  | Pass
14 | UC-4 | Mobile | Select the item of list | If the item of list is selected, detail view of receipt will be shown |  | Pass
15 | UC-4 | Mobile | Long Click on the item of list | Dialog popup will be shown to get confirm to delete the item |  | Pass
16 | UC-5 | Mobile | Check detailed view of receipt | The detailed view will have image of the receipt, store name, date of purchase, category, tag, comment, total, payment method. Edit button will be shown at the bottom |  | Pass
19 | UC-5 | Both | Select one of items for viewing details | At detail, it will show receipt's detail information such as date of purchase, store, category, total, comment, tag, picture of receipt. |  | Pass
20 | UC-6 | Mobile | At mobile, go to the menu of create receipt | The phone will be in preview state of taking picture |  | Pass
21 | UC-6 | Mobile | Check preview screen | There shoule be some feedback to the user to help taking picture of receipt for better character recognition |  | Pass
22 | UC-6 | Mobile | There's menu to take picture | If user select taking picture, result of character recognition for total and store name will be presented to the user And User can edit the information |  | Pass
23 | UC-6 | Mobile | Save the result | After saving the information, there's feedback it was saved succssfully or not and will be redirected to the list of receipt |  | Pass
24 | UC-6 | Mobile | Scan a receipt for a store listed in the autocomplete | After taking photo, the correct store name is found by OCR. |  | Pass
25 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete | After taking photo, the correct payment method is found by OCR. |  | Pass
26 | UC-6 | Mobile | Scan a receipt with a store name not found in the autocomplete | First line of text is suggested as store name |  | Pass
27 | UC-6 | Mobile | Scan a receipt with a store name not found in autocomplete and allow user to add new store name | After taking photo, on Add Receipt screen a store name can be edited and added |  | Pass
28 | UC-6 | Mobile | Scan a receipt and make sure total is found by O.C.R. | The total is found and completed by the O.C.R. |  | Fail
29 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete but change it before saving | The user can change a payment method before saving |  | Pass
30 | UC-6 | Mobile | Make sure the image of a receipt is saved after scanning | Bounding boxes are removed from the image |  | Pass
31 | UC-6 | Mobile | During scanning of image before taking photo, display results found so far for user to see | The displayed indicators should be in synchronization with the ocr result |  | Pass
32 | UC-6 | Mobile | Scan a store name printed with stylized text, logo, etc. | O.C.R. should be able to recognize some special fonts, not always but at least some cases should work. |  | Pass
33 | UC-6 | Mobile | Scan a receipt with a date that includes the month fully written out, i.e. "January", "July", etc. | All parts of the date should be found by the O.C.R. |  | Pass
34 | UC-6 | Mobile | Scan a receipt with a date of format dd-mm-yyyy | The O.C.R. should recognize the '-' delimiter and process the date |  | Pass
35 | UC-6 | Mobile | Scan a receipt with a date of format dd/mm/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Scanning for too few characters produces incorrect results | Fail | No
36 | UC-6 | Mobile | Scan a receipt with a date that includes three letters of the month written out, i.e. "Jan", "Jul", etc. | The O.C.R. should find the date and scan it correctly | Tested with Visa successfully | Pass | Yes
37 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm-dd-yyyy | The O.C.R. should recognize the '-' delimiter and process the date | Works as expected | Pass | Yes
38 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm/dd/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Works as expected | Pass | Yes
39 | UC-7 | Mobile | Select edit button at detail view | Edit screen of the receipt will be shown | Subtotal is sometimes found by mistake. | Fail | No
40 | UC-7 | Mobile | Modify value at edit view and save | Modified value should be applied and it will goto list view | Works as expected | Pass | Yes
41 | UC-6 | Mobile | Cacel the result | If user select cancel instead of save, it will go to the preview status | Image saved but bounding boxes still present | Fail | No
42 | UC-7 | Mobile | At mobile, go to edit recipt information which is presented at list view of receipt or detail view of receipt | User can edit receipt information manually and after saving it will go to previous state. | Data displayed does always update when result changes | Fail | No
43 | UC-7 | Both | After Sync, check the updated information at web app | After sync, updated receipt information can be seen at Web app | Works as exppected | Pass | Yes
44 | UC-8 | Mobile | Delete one of items and check the list of recipt | User can delete one or more receipt at the receipt list or receipt detail | Works as expected | Pass | Yes
45 | UC-9 | Both | Search one recipt with keyword at the search menu box | User can search receipt by keywords | Works as expected | Pass | Yes
46 | UC-9 | Both | Select a filter at the list | User can filter receipt by store, category, date | Works as expected | Pass | Yes
47 | UC-10 | Both | Select Adding Tag at the receipt list | User can add tag at the list of receipt or detail view of receipt | Works as expected | Pass | Yes
48 | UC-10 | Both | Select Addinng Category for the store | There is a menu for adding or modifying store's category | Date not found | Fail | No
49 | UC-13 | Web | Groups, Clicking 'Groups' on the navigation bar | Move to 'Groups' page | Works as expected | Pass
50 | UC-13 | Web | Groups, showing group information | If user has user's already created group, then display group name as owner. If user has joined group(s) as a member, then display joined group(s) name | Works as expected | Pass
51 | UC-13 | Web | Groups, Clicking 'Add Group' button | When user haven't created a group, 'Add Group' button is visible. After clicking 'Add Group' button, move to 'Add Group' page | Works as expected | Pass
52 | UC-13 | Web | Add Group, input group name, group description | Group name is required and description is optional. Validating group name such as empty value and less than 30 letters. Also description is limited less than 140 letters | Works as expected | Pass
53 | UC-13 | Web | Add Group, Clicking 'Save Group' button | Save group name and descript and redirect to 'Groups' page | Works as expected | Pass
54 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as owner' | Move to eighter of 'Group Receipts', 'View Group', or 'Edit Group' pages | Works as expected | Pass
55 | UC-13 | Web | View Group, show group detailed information | display data from database, and show member(s) email list if the group has member(s). If the loggedin user is an owner of group, shows additional buttons such as 'Edit Group', 'Group Categories', 'Group Stores', and 'Group Tags' | Works as expected | Pass
56 | UC-13 | Web | View Group, clicking each of buttons | move to related pages such as 'Group Receipts', 'Group Charts' | Works as expected | Pass
57 | UC-13 | Web | Edit Group, edit group name, description | Group name and description is editable | Works as expected | Pass
58 | UC-13 | Web | Edit Group, 'Delete Group' is disabled | If group already has member(s), owner is not allowed to delete group, so the 'Delete Group' button is disabled | Works as expected | Pass
59 | UC-13 | Web | Edit Group, Clicking 'Invitation' button | Group owner is allowed to invite user as group member with email, after clicking 'Invitation' button, email is added in the 'Invitation list' | Works as expected | Pass
60 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Invitation list' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Invitation list'. When clicking 'Cancel', close the pop up window and back to Edit Group page | Works as expected | Pass
61 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Leaving Group' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Leaving Group'. The member will not show any more When clicking 'Cancel', close the pop up window and back to Edit Group page | Works as expected | Pass
62 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as member' | Move to relevent page in case of 'Receipt' and 'View Details' | Works as expected | Pass
63 | UC-13 | Web | Groups, Clicking 'Leave Group' font icon button in 'Group as member' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, send request notification to group owner. When clicking 'Cancel', close the pop up window and back to Group page | Works as expected | Pass
64 | UC-13 | Web | Groups, Showing notification | Member can receive notification from group owner's invitation as member | Works as expected | Pass

## Iteration4
Schedule
Planned Start Date |  | Planned End Date |  | Actual Start Date |  | Actual End Date
2016-08-01 |  | 2016-08-04
SUM
Total TC | Tested TC (Except N/A) | Total Pass | Total Fail | Total Resolved | Pass Rate | Resolved Rate
58 | 58 | 40 | 6 | 9 | 68.97% | 150%
ID | UseCaseID | Device | Test Case Description | Expected Result | Actual Result Description | Pass/Fail | Resolved
1 | UC-1 | Both | At login screen, check the availability of sign up menu and check the functionality of sign up menu | There is sign up button or link is available and if user select the button, user can enter their information to sign up |  | Pass
2 | UC-1 | Both | If some required field is unfilled, check the submit button | If user miss some required field at the sign up form, submit button should be inactive At mobile, after user select submit, it will be notified required field is not filled |  | Pass
3 | UC-1 | Both | Filling out sign up form and submit the form | There is a message feedback after user successfully submit the register form. After signing up, user can log in the system automatically |  | Pass
4 | UC-1 | Both | After signup at mobile, try to sign in at web app with the same account | User can login at web app |  | Pass
5 | UC-1 | Both | After signup at web app, try to sign in at mobile app with same account | User can login at mobile app |  | Pass
6 | UC-2 | Both | Check functionality of login | User can login with registered email id |  | Pass
7 | UC-2 | Mobile | Check the existence of auto login checkbox | At login form screen, auto login check box should exist |  | Pass
8 | UC-3 | Mobile | If user check auto login checkbox, try to login and Check setting menu | After login successfully, autologin checkbox should be checked |  | Pass
9 | UC-3 | Mobile | Exit with autologin checkbox checked, and try to rerun the app | User can login automatically without asking login ID |  | Pass
10 | UC-3 | Mobile | Uncheck the autologin checkbox and exit the app Run the application and check login screen | User login screen should be shown |  | Pass
11 | UC-3 | Mobile | Reinstall the mobile application and try to login with the same account | User can login with the same account |  | Pass
12 | UC-4 | Mobile | After login, check the screen | At initial state , No Receipt screen will be shown After adding receipt, list of receipt will be shown |  | Pass
13 | UC-4 | Mobile | Check the item of list | Receipt information will have date, store, category, total, tag, receipt image, status of sync |  | Pass
14 | UC-4 | Mobile | Select the item of list | If the item of list is selected, detail view of receipt will be shown |  | Pass
15 | UC-4 | Mobile | Long Click on the item of list | Dialog popup will be shown to get confirm to delete the item |  | Pass
16 | UC-5 | Mobile | Check detailed view of receipt | The detailed view will have image of the receipt, store name, date of purchase, category, tag, comment, total, payment method. Edit button will be shown at the bottom |  | Pass
19 | UC-5 | Both | Select one of items for viewing details | At detail, it will show receipt's detail information such as date of purchase, store, category, total, comment, tag, picture of receipt. |  | Pass
20 | UC-6 | Mobile | At mobile, go to the menu of create receipt | The phone will be in preview state of taking picture |  | Pass
21 | UC-6 | Mobile | Check preview screen | There shoule be some feedback to the user to help taking picture of receipt for better character recognition |  | Pass
22 | UC-6 | Mobile | There's menu to take picture | If user select taking picture, result of character recognition for total and store name will be presented to the user And User can edit the information |  | Pass
23 | UC-6 | Mobile | Save the result | After saving the information, there's feedback it was saved succssfully or not and will be redirected to the list of receipt |  | Pass
24 | UC-6 | Mobile | Scan a receipt for a store listed in the autocomplete | After taking photo, the correct store name is found by OCR. |  | Pass
25 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete | After taking photo, the correct payment method is found by OCR. |  | Pass
26 | UC-6 | Mobile | Scan a receipt with a store name not found in the autocomplete | First line of text is suggested as store name |  | Pass
27 | UC-6 | Mobile | Scan a receipt with a store name not found in autocomplete and allow user to add new store name | After taking photo, on Add Receipt screen a store name can be edited and added |  | Pass
28 | UC-6 | Mobile | Scan a receipt and make sure total is found by O.C.R. | The total is found and completed by the O.C.R. |  | Fail
29 | UC-6 | Mobile | Scan a receipt with a payment method listed in the autocomplete but change it before saving | The user can change a payment method before saving |  | Pass
30 | UC-6 | Mobile | Make sure the image of a receipt is saved after scanning | Bounding boxes are removed from the image |  | Pass
31 | UC-6 | Mobile | During scanning of image before taking photo, display results found so far for user to see | The displayed indicators should be in synchronization with the ocr result |  | Pass
32 | UC-6 | Mobile | Scan a store name printed with stylized text, logo, etc. | O.C.R. should be able to recognize some special fonts, not always but at least some cases should work. |  | Pass
33 | UC-6 | Mobile | Scan a receipt with a date that includes the month fully written out, i.e. "January", "July", etc. | All parts of the date should be found by the O.C.R. |  | Pass
34 | UC-6 | Mobile | Scan a receipt with a date of format dd-mm-yyyy | The O.C.R. should recognize the '-' delimiter and process the date |  | Pass
35 | UC-6 | Mobile | Scan a receipt with a date of format dd/mm/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Scanning for too few characters produces incorrect results | Fail | No
36 | UC-6 | Mobile | Scan a receipt with a date that includes three letters of the month written out, i.e. "Jan", "Jul", etc. | The O.C.R. should find the date and scan it correctly | Tested with Visa successfully | Pass | Yes
37 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm-dd-yyyy | The O.C.R. should recognize the '-' delimiter and process the date | Works as expected | Pass | Yes
38 | UC-6 | Mobile | Reverse the order of day and month, scan a date of format mm/dd/yyyy | The O.C.R. should recognize the '/' delimiter and process the date | Works as expected | Pass | Yes
39 | UC-7 | Mobile | Select edit button at detail view | Edit screen of the receipt will be shown | Subtotal is sometimes found by mistake. | Fail | No
40 | UC-7 | Mobile | Modify value at edit view and save | Modified value should be applied and it will goto list view | Works as expected | Pass | Yes
41 | UC-6 | Mobile | Cacel the result | If user select cancel instead of save, it will go to the preview status | Image saved but bounding boxes still present | Fail | No
42 | UC-7 | Mobile | At mobile, go to edit recipt information which is presented at list view of receipt or detail view of receipt | User can edit receipt information manually and after saving it will go to previous state. | Data displayed does always update when result changes | Fail | No
43 | UC-7 | Both | After Sync, check the updated information at web app | After sync, updated receipt information can be seen at Web app | Works as exppected | Pass | Yes
44 | UC-8 | Mobile | Delete one of items and check the list of recipt | User can delete one or more receipt at the receipt list or receipt detail | Works as expected | Pass | Yes
45 | UC-9 | Both | Search one recipt with keyword at the search menu box | User can search receipt by keywords | Works as expected | Pass | Yes
46 | UC-9 | Both | Select a filter at the list | User can filter receipt by store, category, date | Works as expected | Pass | Yes
47 | UC-10 | Both | Select Adding Tag at the receipt list | User can add tag at the list of receipt or detail view of receipt | Works as expected | Pass | Yes
48 | UC-10 | Both | Select Addinng Category for the store | There is a menu for adding or modifying store's category | Date not found | Fail | No
49 | UC-2 | Web | Login, check input validation of email and password | Invalid input values are not allowed and shows message to User | Works as expected | Pass
50 | UC-2 | Web | Login, 'Log In' button is disable | User input valid value at email and password input box then 'Log In' button turns enable to perform login | Works as expected | Pass
51 | UC-2 | Web | Loggedin successfully | redirect to user dashboard page | Works as expected | Pass
52 | UC-2 | Web | Clicking Logout | User access token is delete and redirect to home page (about page) | Works as expected | Pass
53 | UC-1 | Web | SignUp page | When user clicks SignUp link, move to SignUp page. User resgister with only email and password | Works as expected | Pass
54 | UC-1 | Web | SignUp, Clicking 'SignUp' button | Email, password input values are validate. Invalid value exist, pop-up message will be showing to notify | Works as expected | Pass
55 | UC-5 | Web | Unauthorized user trys to access loggedin pages | redirect to the 'Login' pages | Works as expected | Pass
56 | UC-12 | Web | Dashboard, displaying each data | data retrieve from database correctly, if no data in database show no data in it | Works as expected | Pass
57 | UC-12 | Web | Dashboard, chart can export to several types of tiles | Export chart to Print, PDF, JPEG, PNG, SVG files | Works as expected | Pass
58 | UC-12 | Web | Dashboard, edit user's basic profile and change password | User can modify username, firstname, lastname, user potho, and changing password | Works as expected | Pass
59 | UC-12 | Web | Dashboard, upload user's photo in user profile pop-up window | Only allows image type of file and validate less than 2MB file size, if invalid shows message to user | Works as expected | Pass
60 | UC-12 | Web | Dashboard, clicking each of tag name in Tags cloud section | Pop-up window to show receipts list related with selected tag | Works as expected | Pass
61 | UC-12 | Web | Dashboard, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt | Works as expected | Pass
62 | UC-4 | Web | Receipts, show user's receipt data | retrieve from receipts data from database with pagination | Works as expected | Pass
63 | UC-4 | Web | Receipts, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
64 | UC-4 | Web | Receipts, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
65 | UC-4 | Web | Receipts, Sorted by clicking each table title | Except comment, sorted by store name, data, total, number of items out of receipts list | Works as expected | Pass
66 | UC-4 | Web | Receipts, Export Excel file function | When user clicks 'Export Excel' icon, downloading the excel file including contents of table | Works as expected | Pass
67 | UC-5 | Web | View Receipt, Show data and image of receipt | Display data from database, and show image of photo if attached | Works as expected | Pass
68 | UC-5 | Web | View Receipt, clicking 'Edit button' | Move to Edit Page with related data of the receipt | Works as expected | Pass
69 | UC-5 | Web | View Receipt, clicking 'Tag's button related with the receipt | Pop-up window to show receipts list related with selected tag | Works as expected | Pass
70 | UC-5 | Web | View Receipt, 'Receipts in Tag' modal window | has functions of search filtering, export excel file, sorting as title, and pagination which work correctly as receipts page does. And move to View Receipt page when clicking view detail icon of each receipt | Works as expected | Pass
71 | UC-6 | Web | Add Receipt, Data editable | Store, Category, Price, Number of items are required and validation check. Comment is optional, but only allowed 140 letters length. Other required input value will be validated, when invalid value exist, pop-up message to notice. | Works as expected | Pass
72 | UC-6 | Web | Add Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Works as expected | Pass
73 | UC-7 | Web | Edit Receipt, Data editable | Store, Category, Price, Number of items, comment, image of receipt are editable | Works as expected | Pass
74 | UC-7 | Web | Edit Receipt, Clicking 'Save Receipt' button | Store data into database and return to View Receipt page to confirm edited data | Works as expected | Pass
75 | UC-8 | Web | Edit Receipt, Clicking 'Delete Receipt' button | pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete receipt and remove relation with related with data and then redirect to 'Receipts' page. When clicking 'Cancel', close pop up window and back to Edit Receipt page | Works as expected | Pass
76 | UC-7 | Web | Edit Receipt, validation of input values | Editable values are validated where each of values is valid or not | Works as expected | Pass
77 | UC-7 | Web | Edit Receipt, uploading image file of receipt | Allow image type files are allowed to be uploaded and validate less than 2MB file size | Works as expected | Pass
78 | UC-11 | Web | Chart, Clicking 'chart' menu link in the navigation bar | Move to 'Charts' page and display various type of chars and graphs. Monthly consumption, Comparison bar chart, Tag tendency, Store Amount, Category, Store, Tag, and Tag Progress Bar chart which are all retrived from database | Works as expected | Pass
79 | UC-11 | Web | Chart, Changing the period of month in 'Montly consumption' title bar | Changing all charts and graphs according to selected period of months and display data that retrieve from database | Works as expected | Pass
80 | UC-11 | Web | Chart, Moving mouse on the each value of chart or graph | Pop up the tooltip and show the value of each chart or graph | Works as expected | Pass
81 | UC-11 | Web | Chart, Clicking pdf icon button on the right top of the title bar | Download pdf file as selected chart in Monthly comsumption, Comparison, Tag Tendancy, and Store Amount Charts | Works as expected | Pass
82 | UC-10 | Web | Categories, clicking 'Config-Categories' menu in the navigation bar | Shows user's customizing category data which retrieved from database with pagination | Works as expected | Pass
83 | UC-10 | Web | Categories, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
84 | UC-10 | Web | Categories, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
85 | UC-10 | Web | Categories, Sorted by clicking category name | sorted by category name as descending or ascending | Works as expected | Pass
86 | UC-10 | Web | Categories, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected category | Works as expected | Pass
87 | UC-10 | Web | Categories, Clicking 'Add Category' button | Move to Add Page | Works as expected | Pass
88 | UC-10 | Web | Add Category, input category name | User is allow to input category name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
89 | UC-10 | Web | Add Category, Clicking 'Save Category' button | if category name is valid, 'Save Category' button is enabled, after clicking 'Save Category' button, store new category name into database, and then redirect to 'Categories' page | Works as expected | Pass
90 | UC-10 | Web | Edit Category, 'Delete Category' button is disabled | When category is used by store(s), user is not allowed to delete category, so 'Delete Category' button is disabled | Works as expected | Pass
91 | UC-10 | Web | Edit Category, Edit Category Name | Category Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
92 | UC-10 | Web | Edit Category, Clicking 'Save Category' button | Save category name and redirect to 'Categories' page | Works as expected | Pass
93 | UC-10 | Web | Edit Category, Clicking 'Delete Category' | When clicking enabled 'Delete Category', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete catgory and then redirect to 'Categories' page. When clicking 'Cancel', close the pop up window and back to Edit Category page | Works as expected | Pass
94 | UC-10 | Web | Tags, clicking 'Config-Tags' menu in the navigation bar | Shows user's customizing tag data which retrieved from database with pagination | Works as expected | Pass
95 | UC-10 | Web | Tags, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
96 | UC-10 | Web | Tags, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
97 | UC-10 | Web | Tags, Sorted by clicking category name | sorted by tag name as descending or ascending | Works as expected | Pass
98 | UC-10 | Web | Tags, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected tag | Works as expected | Pass
99 | UC-10 | Web | Tags, Clicking 'Add Tag' button | Move to Add Page | Works as expected | Pass
100 | UC-10 | Web | Add Tag, input tag name | User is allow to input tag name, but validate invalid input value such empty value, already existing name | Works as expected | Pass
101 | UC-10 | Web | Add Tag, Clicking 'Save Tag' button | if tag name is valid, 'Save Tag' button is enabled, after clicking 'Save Tag' button, store new tag name into database, and then redirect to 'Tags' page | Works as expected | Pass
102 | UC-10 | Web | Edit Tag, 'DeleteTag' button is disabled | When tag is used by receipt(s), user is not allowed to delete tag, so 'Delete Tag' button is disabled | Works as expected | Pass
103 | UC-10 | Web | Edit Tag, Edit Tag Name | Tag Name is editable, but validate invalid input value such empty value, already existing name | Works as expected | Pass
104 | UC-10 | Web | Edit Tag, Clicking 'Save Tag' button | Save tag name and redirect to 'Tags' page | Works as expected | Pass
105 | UC-10 | Web | Edit Tag, Clicking 'Delete Tag' | When clicking enabled 'Delete Tag', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete tag and then redirect to 'Tags' page. When clicking 'Cancel', close the pop up window and back to Edit Tag page | Works as expected | Pass
106 | UC-10 | Web | Stores, clicking 'Config-Stores' menu in the navigation bar | Shows user's customizing store data which retrieved from database with pagination | Works as expected | Pass
107 | UC-10 | Web | Stores, pagination function | Previous and Next button work correctly, page unit works correctly | Works as expected | Pass
108 | UC-10 | Web | Stores, Search function | When user input value in search text, it filters and show the result in the table correctly | Works as expected | Pass
109 | UC-10 | Web | Stores, Sorted by clicking store name | sorted by store name as descending or ascending | Works as expected | Pass
110 | UC-10 | Web | Stores, Clicking 'Edit' font icon button | Move to Edit Page with related data of selected store | Works as expected | Pass
111 | UC-10 | Web | Stores, Clicking 'Add Store' button | Move to Add Page | Works as expected | Pass
112 | UC-10 | Web | Add Store, input store name | User is allow to input store name and select category, but validate invalid input value such empty value, already existing name, and if category is selected or not | Works as expected | Pass
113 | UC-10 | Web | Add Store, Clicking 'Save Store' button | if store name is valid, 'Save Store' button is enabled, after clicking 'Save Store' button, save new store name with relation to category into database, and then redirect to 'Stores' page | Works as expected | Pass
114 | UC-10 | Web | Edit Store, 'Delete Store' button is disabled | When store is used by receipt(s), user is not allowed to delete store, so 'Delete Store' button is disabled | Works as expected | Pass
115 | UC-10 | Web | Edit Store, Edit Store Name and select category name | Store name is editable and allow to re-select category accordingly, but validate invalid input value such empty value, already existing name, and if category is selected or not | Works as expected | Pass
116 | UC-10 | Web | Edit Store, Clicking 'Save Store' button | Save store name and redirect to 'Stores' page | Works as expected | Pass
117 | UC-10 | Web | Edit Store, Clicking 'Delete Store' | When clicking enabled 'Delete Store', pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, delete store with disconnecting relation to category and then redirect to 'Stores' page. When clicking 'Cancel', close the pop up window and back to Edit Store page | Works as expected | Pass
118 | UC-13 | Web | Groups, Clicking 'Groups' on the navigation bar | Move to 'Groups' page | Works as expected | Pass
119 | UC-13 | Web | Groups, showing group information | If user has user's already created group, then display group name as owner. If user has joined group(s) as a member, then display joined group(s) name | Works as expected | Pass
120 | UC-13 | Web | Groups, Clicking 'Add Group' button | When user haven't created a group, 'Add Group' button is visible. After clicking 'Add Group' button, move to 'Add Group' page | Works as expected | Pass
121 | UC-13 | Web | Add Group, input group name, group description | Group name is required and description is optional. Validating group name such as empty value and less than 30 letters. Also description is limited less than 140 letters | Works as expected | Pass
122 | UC-13 | Web | Add Group, Clicking 'Save Group' button | Save group name and descript and redirect to 'Groups' page | Works as expected | Pass
123 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as owner' | Move to eighter of 'Group Receipts', 'View Group', or 'Edit Group' pages | Works as expected | Pass
124 | UC-13 | Web | View Group, show group detailed information | display data from database, and show member(s) email list if the group has member(s). If the loggedin user is an owner of group, shows additional buttons such as 'Edit Group', 'Group Categories', 'Group Stores', and 'Group Tags' | Works as expected | Pass
125 | UC-13 | Web | View Group, clicking each of buttons | move to related pages such as 'Group Receipts', 'Group Charts' | Works as expected | Pass
126 | UC-13 | Web | Edit Group, edit group name, description | Group name and description is editable | Works as expected | Pass
127 | UC-13 | Web | Edit Group, 'Delete Group' is disabled | If group already has member(s), owner is not allowed to delete group, so the 'Delete Group' button is disabled | Works as expected | Pass
128 | UC-13 | Web | Edit Group, Clicking 'Invitation' button | Group owner is allowed to invite user as group member with email, after clicking 'Invitation' button, email is added in the 'Invitation list' | Works as expected | Pass
129 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Invitation list' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Invitation list'. When clicking 'Cancel', close the pop up window and back to Edit Group page | Works as expected | Pass
130 | UC-13 | Web | Edit Group, Clicking 'Remove' font icon in the 'Leaving Group' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, remove email in the 'Leaving Group'. The member will not show any more When clicking 'Cancel', close the pop up window and back to Edit Group page | Works as expected | Pass
131 | UC-13 | Web | Groups, Clicking each of font icon button in 'Group as member' | Move to relevent page in case of 'Receipt' and 'View Details' | Works as expected | Pass
132 | UC-13 | Web | Groups, Clicking 'Leave Group' font icon button in 'Group as member' | Pop-up a window to confirm 'OK' or 'Cancel'. When Clicking 'OK' button, send request notification to group owner. When clicking 'Cancel', close the pop up window and back to Group page | Works as expected | Pass
133 | UC-13 | Web | Groups, Showing notification | Member can receive notification from group owner's invitation as member | Works as expected | Pass
134 | UC-13 | Web | Groups, Clicking each of font icon button in 'Invitation' section | Accept', 'View Group', 'Refuse Invitation' action will be performed accordingly by user | Works as expected | Pass
135 | UC-13 | Web | Groups, Showing notification from member request leaving | when member requests leaving group, group own can show the list of member's request for leaving | Works as expected | Pass
136 | UC-13 | Web | Groups, Clicking edit font icon button in 'Leaving Request' section | Group owner can take action for member's request for leaving | Works as expected | Pass